# GNSO 4 month Operational Plan

# 1 March – 30 June 2006

## Section 1 - Current Projects

| Work item, project number, priority, lead Councilor / Staff, relevant documents | Current status / Next action | Milestones | Project on schedule / comments |
| --- | --- | --- | --- |
| New gTLDs Project No. 2005 / 01 Priority 1 Staff lead: Olof Nordling Relevant documents: Call for Papers on the Policy Development for the Introduction of New gTLDs http://www.icann.org/announcements/announcement-03jan06.htm GNSO Discussion Document; additional evaluation of new TLDs Circulated to Council mailing list 9 November 2005: http://gnso.icann.org/mailing-lists/archives/council/msg01518.html Draft GNSO Issues Report on Introduction of New TLDs, circulated to Council mailing list 8 November 2005: http://gnso.icann.org/mailing-lists/archives/council/msg01507.html | 29 March 2006 GNSO Council meeting (Wellington) 16 March 2006 Conclusion of public comment period on draft Initial Report 24-25 February 2006 Inter-sessional working days on new TLD PDP, Washington D.C. 14 February 2006 GNSO DRAFT Initial Report -- Introduction of New Generic Top-Level Domains published for public comments from 20 February to 13 March 2006 31 January 2005 End of public comment period on launch of PDP 3 January 2006 Publication of a Call for Papers on policy development for introduction of new gTLDs (deadline was 31 January, 2006) 8 December – 31 January 2006 Call for constituency statements 21 December 2005 Council decided to extend the deadline to allow for substantive papers with input on the terms of reference of the PDP. 6 December 2005 Beginning of public comment period following notification of the initiation of the PDP. 28 November 2005 GNSO Council voted to launch a PDP. | 25 – 27 May 2006 Working meeting in Brussels ? 2006 Submission of Final Report to GNSO Council ? 2006 GNSO Council meeting to discuss the report and work toward achieving a supermajority vote on a recommendation to present to the Board. | Behind schedule - 3 weeks Due to extension of deadline for public comment and constituency statements from 9 January 2006 to 31 January 2006. |
| GNSO Review Project No. 2005/02 Priority 1 Staff lead: Liz Williams Relevant documents: | 30 January 2006 Appointment of independent consultant 2 January 2006 Deadline for proposals from evaluators 10 December 2005 Released Terms of Reference and Request for Proposal for Evaluators 4 December 2005 Vancouver Board meeting. Approval of Terms of Reference and resolution to proceed with GNSO Review | 24 – 30 March 2006 (Wellington meeting) GNSO reviewers conducting interviews at community meetings at Wellington meeting. | On schedule |
| GNSO work on Internationalized Domain Names (IDNs) Project No. 2005 / 03 Priority 1 Staff lead: Tina Dam / Maria Farrell Relevant documents: Review and Recommendations for IDN, draft IAB/IETF next steps John Klensin / Patrik Fältström http://www.ietf.org/internet-drafts/draft-iab-idn-nextsteps-04.txt ‘GNSO Policy Development for IDNs: Background Paper’ Circulated to Council mailing list on 28 October, 2005: http://gnso.icann.org/mailing-lists/archives/council/msg01479.html | 17 January 2006 Council heard information from John Klensin and Patrik Fältström on IAB/IETF work on IDN 2 December 2005 GNSO Council resolved: “WHEREAS, the GNSO Council recognises that one of the goals of ICANN to increase the internationalisation of the domain name space; WHEREAS, the GNSO Council wishes to liaise closely with the ccNSO with respect to internationalization of the domain name space, and for the purpose of jointly requesting an issues report; WHEREAS the GNSO Council recognizes and wishes to inform and be informed by the technical efforts currently under way in other organizations which are represented on the President’s Advisory Committee on IDNs; WHEREAS the GNSO Council acknowledges the timelines in the ICANN bylaws, and recognize the recommendation from the GNSO Council review to revise those timelines, and given the complexity of this issue, the GNSO Council will develop an appropriate work plan that meets the needs of the ICANN community. The GNSO Council requests an Issues Report on the policy issues associated with creating internationalised equivalents of existing gTLDs, and second level domains within existing gTLDs. The GNSO Council recommends that the staff engage appropriate expert resources to assist in the preparation of the Issues Report. The GNSO also requests that the staff liaise with the ccNSO to ensure that the policy issues associated with internationalised versions of the existing ccTLDs can also be considered. | . Date TBA Staff submits Issues Report to GNSO Council Date TBA Meeting date of GNSO Council TBA GNSO Council vote on whether to launch a PDP. Decision on how to execute the PDP (e.g. to create and populate a task force). If a task force is created: Date TBA Develop a Task Force Charter or Terms of Reference (see Annex A, section 7 of ICANN Bylaws for charter content) Date TBA Task force to convene and vote to appoint TF chair. Date TBA Call for constituency statements Public comment period Date TBA Submission by staff of Preliminary Task Force Report to Task Force. Date TBA Task Force vote on Preliminary Task Force Report. Date TBA Publication of Preliminary Task Force Report for public comments Date TBA Conclusion of public comment period Date TBA Submission of Final Task Force Report to GNSO Council Date TBA GNSO Council meeting (Wellington) to discuss the report and work toward achieving a supermajority vote to present to the Board. |  |
| Transfers Working Group Project No. 2005 / 04 Priority 2 GNSO Council lead: Ross Rader Staff lead: Karen Lentz Mike Zupke Maria Farrell Relevant documents: | 29 March 2006 Ross Rader to report to GNSO Council on progress and next steps. 17 March 2006 Ross Rader circulated to working group an updated reference document. 19 January 2006 ICANN staff distributed overview of issues raised in the transfers working group, with suggested next steps |  |  |
| Purpose of Whois & Whois Contacts Project No. 2005 / 05 Project No. 2005 / 06 Priority 1 Staff lead: Maria Farrell | 17 March 2006 Final Task Force Report submitted to the GNSO Council. 18 January 2006 Preliminary Task Force Report on purpose of Whois and Whois contacts published for public comments from 19 January 2006 to 08 February 2006 17 January 2006 Whois Task Force voted on Preliminary Task Force Report on Purpose of Whois & Whois Contacts. 18 January – 7 February, 2006 Public comment period on Preliminary Task Force Report on Purpose of Whois & Whois Contacts. | 12 April 2006 Consideration by GNSO Council of Final Task Force Report on Purpose of WHOIS |  |
| WHOIS Rec. 1 on improved notification and consent Project No. 2005 / 07 Priority 1 Staff lead: Maria Farrell | 29 March 2006 GNSO Council decision on Final Task Force Report on improved Whois notification and consent. Staff to provide updated information on legal clarification of notification versus consent. |  |  |
| WHOIS Rec. 2 on a policy and procedure national laws Project No. 2005 / 07 Priority 1 Staff lead: Maria Farrell Relevant documents: 'Final task force report on a policy recommendation and advice on a procedure for handling conflicts between a registrar/registry's legal obligations under privacy laws and their contractual obligations to ICANN' Circulated to Council mailing list on 28 October, 2005: http://gnso.icann.org/mailing-lists/archives/council/msg01480.html | 18 January 2006 GNSO Board Report posted for information on the ICANN website. 12 January 2006 GNSO reviewed and approved (on-list) Board Report prepared by staff. 28 November 2005 GNSO Council to considered Final Task Force Report and voted to accept its recommendation. | Next step: Board to consider the GNSO recommendation. (expected April 2006) |  |
| WHOIS Accuracy Working Group Project No. 2005 / 08 Priority 2 Council lead: Niklas Lagergren (IPC) Staff lead: Maria Farrell | 29 March 2006 (Wellington meeting) Ross Rader to report on the group’s progress. 23 January 2006 Staff circulated to Accuracy Group a meeting summary that discusses next actions. Niklas Lagergren to circulate schedule of next actions. 11 January 2006 Accuracy Group met and discussed proposals by Bruce Tonkin. Niklas Lagergren to prepare draft schedule and way forward and circulate to the group. | 28 June 2006 (Marrakesh meeting) Accuracy group expects to present findings/recommendations |  |
| ICANN Strategic and Operational Planning Process Project No. 2005 / 09 Priority 1 Council lead: Marilyn Cade / Ross Rader Staff lead: Maria Farrell |  | Date TBA Future participation by GNSO Councillors in ICANN Strategic and Operational Planning Process | Currently on schedule |
| February 2006 PDP on contractual conditions in gTLDs Project No. 2006 /01 Priority 1 Staff lead: Liz Williams 16/17 February 2006 Council Resolution Council unanimously passed the following motion: "The Council resolves: That the Council wishes to appoint a task force for the PDP initiated on 6 February 2006 (PDP-Feb06) that consists of the full Council, including the Council members appointed by the Nominating Committee, the At Large Advisory Committee (ALAC) and the Government Advisory Committee (GAC) liaisons. That constituencies have the option to appoint representatives to the task force in place of their Council members. That the Council recommends that the constituencies ensure that there is at least one council member from the constituency on the task force. That Council members, who are not members of the task force, have observer status on the task force, and thus receive mail from the mailing lists and be able to attend task force calls and meetings as observers." | 29 March 2006 Task force Charter confirmed and task force timeline agreed appointed (Maureen Cubberley) 10 March 2006 Appointment of Task force Representatives and notification of representatives to Secretariat 7 March 2006 – 30 April 2006 Public comment period 16/17 February 2006 Council resolved to appoint a task force for the PDP. 6 February 2006 Council initiated a PDP. 17 January 2006 Council voted to request staff to produce an “Issues Report related to the dot COM proposed agreement in relation to the various views that have been expressed by the constituencies.” | 30 April 2006 Constituency statements due, public comment period closes. 26 May 2006 Preliminary Initial Report released 9 June 2006 Task force meeting to discuss Initial Report 16 June 2006 Updated Initial Report released to GNSO Council for discussion at Marrakech meeting 24-30 June 2006 ICANN meeting Marrakech – TF meeting within ICANN meeting schedule | Currently on schedule |

## Section 2

## Non-active projects - approved but not resourced

| Work item, relevant documents | Current status | Notes |  |
| --- | --- | --- | --- |
| Contention for domain names at gtld registries | Work item agreed by Council resolution but not currently resourced. 13 January 2005 Council resolution Resolution passed: “Council resolves, to request the ICANN staff manager to write an issues report (as specified in annex A to the ICANN by-laws) on the "Problems caused by contention for domain names made available by a gTLD registry ", so that Council can subsequently decide if a policy development process would be appropriate”. | Council needs to consider whether/how work on RGP relates to this existing resolution. (staff note, 24 March 2006) |  |

## Section 3

## Projects proposed but not yet approved: policy

Insert ‘Proposed update of the rules of procedures’, including issues that need to be discussed.

Separate this section into administrative and policy areas

Single letter 2nd level domain names Council lead: Marilyn Cade Staff lead: Maria Farrell Relevant documents: ‘Status report on single letter domain names’ Circulated to Council mailing list on 14 September 2005

Explore use of Wikis to support GNSO Council collaborative work online Council lead: Aleck Wilson

GNSO Council Review, recommendation 1 The Council has made a significant contribution to other ICANN core values such as outreach, bottom-up consensus based policy development, geographical diversity and transparency. It has endeavoured to make good use of the ICANN meetings to conduct outreach activities with other ICANN organizations and with the broader internet community. The Council should plan to expand and enhance these activities.

GNSO Council Review, recommendation 2 The appointment of liaisons is a good step in building links with other parts of the ICANN structure. Again consideration needs to be given to the best way that these liaisons can be used to raise awareness of Council issues. The crafting of a “role description” or “partnership agreement” may assist with setting clear expectations and maximizing outcomes.

GNSO Council Review, recommendation 3 Develop a plan for increasing representation to cover all regions.

GNSO Council Review, recommendation 4 Consider how people from non-English speaking backgrounds can participate more actively in Council.

GNSO Council Review, recommendation 5 Develop and seek Board approval for a revised Policy Development Process.

GNSO Council Review, recommendation 6 Develop a formal process for seeking input from other ICANN organizations for each of the policies it is developing.

GNSO Council Review, recommendation 7 Consider other measures to speed up the consensus process, including the greater use of time at ICANN meetings to discuss issues face to face, and possibly the use of facilitators to move more quickly to understanding of issues and building of consensus.

GNSO Council Review, recommendation 8 Chair of the GNSO Council and the VP Supporting Organizations should establish a service level agreement between the GNSO Council and ICANN management that specifies the amount and type of support that is to be provided. Where possible, this should include measures (eg turnaround times for legal opinion, delivery of reports by agreed dates, minutes posted within a certain number of days) The Chair should consult the Council to ensure the targets meet the needs of the Council and its taskforces. The VP Supporting Organizations and Chair of GNSO Council should meet quarterly to review performance measures and report these to the President.

GNSO Council Review, recommendation 9 Council should work with the ICANN General Counsel to establish clear communication channels for the request for and provision of legal opinion. At a minimum this should include detailed legal input at the scoping phase of each PDP. Wherever possible, “check points” for further legal input should be established as part of the scoping study.

GNSO Council Review, recommendation 12 Ensure the viability of implementation of each of the policy recommendations that it makes to the Board.

GNSO Council Review, recommendation 14 Work with ICANN operational staff to develop a compliance policy with graded penalties.

GNSO Council Review, recommendation 16 GNSO Council should utilize the Ombudsman and any reports produced by the Ombudsman as source of systematic analysis of complaints and therefore of issues that may need to be addressed through the PDP.

GNSO Council Review, recommendation 17 Continue to explore ways in which the Nominating Committee members can add value to the Council process.

GNSO Council Review, recommendation 18 Draft “role descriptions” for the Nominating Committee which describe the skills, expertise (especially technical expertise) and attributes that are needed for the Nominating Committee members to be optimally effective members of the Council.

## Section 4

## Projects proposed but not yet approved: administrative/procedural

Revise and agree GNSO Rules of Procedure Council lead: Bruce Tonkin