TABLE OF CONTENTS (click on the link below to go directly to the project in this list).

.

| Category | Title | Abbreviation |
| --- | --- | --- |
| GNSO WG/DT | GNSO Improvements Standing Committee on Improvement Implementation | SCI |
| GNSO WG/DT | Drafting Team on Cross-Community Working Groups | CWG-DT |
| GNSO WG/DT | IRTP Part D PDP Working Group | IRTP Part D |
| GNSO WG/DT | Policy & Implementation Working Group | PI |
| GNSO WG/DT | GNSO Metrics & Reporting WG (Uniformity of Reporting) | MetRep |
| GNSO WG/DT | RAA Privacy & Proxy Services Accreditation Issues | P&P |
| GNSO WG/DT | Translation/Transliteration of Internationalized Registration Data | T&T |
| Other | WHOIS Studies | WHO1 |
| Other | Purpose of Whois Issue Report | Whois PDP |
| Other | ‘Thick’ WHOIS PDP Working Group | Thick WHOIS |
| Other | Protection of Intergovernmental Organization Names in All gTLDs | IGO-INGO |
| Other | Issue Report on curative protections of the UDRP/URS for IGO/INGOs |  |
| Other | Uniform Dispute Resolution Policy (COMPLETED FOR NOW) | UDRP |
| Joint WG/DT | Geo Regions Review Community-wide Working Group | GEO |
| Joint WG/DT | Joint ccNSO-GNSO Internationalized Domain Names Working Group (JIG) | JIG |
| Joint WG/DT | Joint Security and Stability Analysis Community Drafting Group (DNS Cert) | DSSA |
| Implementation | IRTP Part B Adopted Recommendations | IRTP Part B |
| Implementation | Inter-Registrar Transfer Policy Part C PDP | IRTP Part C |
| Implementation | Locking of a domain name subject to UDRP proceedings | Lock |

Last updated: 4 December 2013

This list includes GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| GNSO Working Groups / Work Teams / Drafting Teams |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| GNSO Standing Committee on Improvements Implementation (SCI) Chair: Ron Andruff Vice-Chair: Avri Doria Staff: J. Hedlund, M. Wong, M. Konings The GNSO Standing Committee on Improvements Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. It was recently confirmed as a standing committee by the GNSO Council. | 2011-Apr-07 | Ongoing | SCI | The SCI is working on the following topics: Working Group survey; Re-submitting a motion; Voting by email; Waiver under the GNSO Operating Procedures; The Council approved a revised Charter at its meeting on 31 October. It did not change decision-making methodology, but may do so in the future. On 20 November, the Council approved the IGO-INGO WG consensus recommendation to have the SCI review the consensus scale definitions in the current WG Guidelines. |
| Cross-Community Working Groups Framework Drafting Team Discussion leader: J. Robinson Staff: M. Wong, J. Hedlund A new CWG Framework drafting team will be formed to further refine the principles for cross-community working groups. | 19 May 2011 | Ongoing | Staff/J. Robinson | At its meeting on 10 October 2013, the GNSO Council passed a motion to establish a new CWG Framework Drafting Team that would include members from the other SOs and ACs, to be co-chaired by the GNSO and ccNSO. On 10 November 2013 ICANN Staff published a paper summarizing the original Drafting Team Principles and the ccNSO feedback, and recommending next steps for the new DT. GNSO Council Chair has written to the other SO/AC chairs soliciting their participation in the new DT and has followed up with a suggestion that the new CWGs being formed to assist the President’s Strategy Panels may wish to utilize the Drafting Team Principles. |
| IRTP Part D PDP WG Co-Chair: James Bladel, Mikey O’Connor Council Liaison: Volker Greimann Staff: L. Hoffmann, M. Konings. PDP on the remaining IRTP issues which include: Reporting requirements for registries and dispute providers in relation to the TDRP; How to handle disputes when multiple transfers have occurred in the TDRP; Should dispute options for registrants be developed; Should there be requirements or best practices for registrars to make information on transfer dispute resolution options available; Are existing penalties for policy violations sufficient; Have EPP AuthInfo codes eliminated the need for FOAs. | 17 Oct 2012 | Ongoing | WG | The WG held its first meeting on 25 February and will continue to meet on a weekly basis. The WG reached out to the community and has finished reviewing the received input. The WG is now in the process of drafting its initial recommendations and has agreed on draft recommendation for four of the six charter questions successfully so far. It will continue its substantive works focussing specifically on changes to the TDRP. The goal for the publication of the Initial Report is currently set for December 2013 / January 2014. |
| Policy & Implementation WG Co-Chairs: Chuck Gomes, J. Scott Evans Council Liaison: TBC Staff: M. Konings, M. Wong The WG is tasked to provide the GNSO Council with a set of recommendations on: A set of principles that would underpin any GNSO policy and implementation related discussions A process for developing gTLD policy, perhaps in the form of “Policy Guidance”, including criteria for when it would be appropriate to use such a process (for developing policy other than “Consensus Policy”) instead of a GNSO Policy Development Process; A framework for implementation related discussions associated with GNSO Policy Recommendations; Criteria to be used to determine when an action should be addressed by a policy process and when it should be considered implementation, and; Further guidance on how GNSO Implementation Review Teams are expected to function and operate. | 9 May 2013 | Ongoing | WG | Following from the work plan sub-team’s initial work on mapping out the different activities, a second sub-team was formed to develop a set of working definitions that will inform the WG’s discussions and tasks as identified in the final work plan. Another sub-team has been formed to develop working principles for the WG. The WG published a set of initial questions for community feedback at its scheduled meeting in Buenos Aires. The work plan has been submitted for final approval at the next WG meeting; the Definitions and Working Principles sub-teams are meeting on a regular basis to finalize their initial recommendations for presentation to the full WG. |
| GNSO Metrics & Reporting DT (Uniformity of Reporting) Chair: M. O’Conner Staff: B. Cobb, L. Hoffmann The WG is tasked to provide the GNSO Council with a set of recommendations on: A set of principles that may compliment any GNSO policy efforts related to metric/data requirements to better inform the policy development process; A process for requesting metrics and reports both internal to ICANN or external, including GNSO contracted parties; A framework for distributing metrics and reports to Working Groups, the GNSO Council and the GNSO as a whole; Changes, if any, to existing Working Group Guidelines and work product templates | 17 Oct 2012 | On-going | DT | At its May 2013 meeting, the GNSO Council approved a motion to form a Drafting Team developing a charter for a non-PDP Working Group considering additional methods for collecting necessary metrics and reporting from Contracted Parties and other external resources. The DT is meeting weekly to complete the MetRep charter. The DT envisages that it will submit the Charter to the GNSO Council in January 2014. |
| RAA Privacy & Proxy Services Accreditation Issues PDP Chair(s): TBC Staff: M. Wong, M. Konings Council Liaison: Maria Farrell The Registrar Accreditation Agreement (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which have been identified as those relating to privacy & proxy services and their accreditation, will be examined in this PDP. | 2009 May-21 | Ongoing | WG | The GNSO Council adopted a charter for the PDP WG at its meeting on 31 October 2013. A call for volunteers was issued and an informal meeting was held in Buenos Aires. The WG held its first formal meeting on 3 December, and will start working on the development of a Work Plan. The WG is expected to elect Chair(s) and Vice-Chair(s) at its next meeting on 10 December. |
| Translation/Transliteration of Internationalized Registration Data PDP WG Chair(s): TBC Council Liaison: Ching Chiao Staff: J. Hedlund/L. Hoffmann The Council approved the initiation of a PDP on translation and transliteration of contact information on 13 June 2013. | 17 Oct 2012 | Ongoing | Council | The GNSO Council approved the PDP WG Charter at its 20 November meeting. The call for volunteers was sent out on 27 November and a webinar will be held on the 10th and 11th of December. The WG will be formed following the Webinars and when a broad selection of volunteers have joined the WG |

| Other GNSO Activities |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| STUDIES |
| WHOIS Studies Staff: Mary Wong The GNSO Council approved several studies of WHOIS. Topics include Misuse of WHOIS Data, Registrant Identification Information, Proxy and Privacy “Abuse” and Proxy and Privacy “Relay” and “Reveal”. Budget was approved by the ICANN Board for these studies. | 2007 Oct-31 | Ongoing | Staff | Staff is overseeing four studies of WHOIS as requested by the GNSO, the last of which are now nearing completion: A Misuse of Public gTLD WHOIS Data Study – conducted by researchers at Carnegie Mellon University (CMU). The study was released for public comment on 27 November 2013. CMU will conduct a webinar during the public comment period. A Registrant Identification Study –launched in October 2011, with draft analysis by NORC. A webinar with summary findings was held on 6 March. The Final Report has been published. A Proxy/ Privacy “Abuse” Study – conducted by the National Physical Lab of the UK (NPL). The study was released for public comment on 24 September 2013. Staff is in the process of analysing the public comments received with the NPL team, with a view to publishing a final report before the end of 2013. A pre-study “survey” on Proxy/Privacy “Relay” and “Reveal” – final report [PDF, 1.23MB] has been published and this study is now completed. |

| AWAITING COUNCIL ACTION |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Joint Security and Stability Analysis Community Working Group (DNS Cert) ccNSO Co-Chair: Jörg Schweiger, .de GNSO Co-Chair: M. O’Connor Staff: B. Boswinkel, J. Hedlund | June 2010 | 12 Dec 2013 | Council | The DSSA has submitted its Final Phase 1 Report to its respective Chartering organizations and a letter to ask them to consider closing the WG. A motion is being prepared for the GNSO Council to consider at its meeting on 12 December that would adopt the Final Report of the DSSA and thank the volunteers for their efforts. |
| Geo Regions Review Community-wide Working Group Chair: Dave Archbold (ccNSO) GNSO Council Reps: Zahid Jamil and Ching Chiao Staff: R. Hoggarth This Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions. Changes could have broad impact, so this WG has representatives from most SOs and ACs. | 7 Aug 2008 | 31 Dec 2013 | Council | The Working Group has published its Final Report recommendations (see - http://www.icann.org/en/news/announcements/announcement-22jun13-en.htm) The Final Report was been circulated to all ICANN SOs and ACs (including the Council) for review and comment. Comments (if any) were due to the Working Group on 17 October 2013). The Council did not submit comments to the WG. Through staff, the WG Chair has followed-up with a note to the GNSO Council Chair and other community leaders noting that the WG Charter requires a written response from communities that supported the WG. The follow-up note supplied a draft template to achieve that end. After written responses are submitted the Final Report of the WG can be shared with the Board. |

| Staff Implementation |
| --- |
| Issue Report on the purpose of collecting and maintaining gTLD registration data and on solutions to improve accuracy and access to gTLD registration data. Staff: M. Wong, M. Konings, L. Hoffmann | 2012-Nov-8 |  | Staff | The Board resolution on the Whois RT Recommendations (see http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm) directs preparation of an Issue Report on the purpose of collecting and maintaining gTLD registration data, and on solutions to improve accuracy and access to gTLD registration data, as part of a Board-initiated GNSO policy development process. The Preliminary Issue Report was published for public comment on 15 March 2013. The comment forum closed on 13 May. A Final Issue Report will be published following the finalization of the EWG recommendations. |
| ‘Thick’ WHOIS PDP WG Chairs: Mikey O’Connor Council Liaison: Volker Greimann Staff: M. Konings, B. Cobb As recommended by the IRTP Part B Working Group, the GNSO Council requested ICANN Staff to prepare an Issue Report on the requirement of ‘thick’ WHOIS for all incumbent gTLDs. At its meeting in Costa Rica, the GNSO Council initiated the PDP. | Nov 2012 |  | Staff / Board | The GNSO Council adopted the WG’s full consensus recommendations at its 31 Oct 2013 meeting. A public comment period is now open until 28 Dec 2013 as a requirement prior to ICANN Board’s consideration. http://www.icann.org/en/news/public-comment/thick-whois-recommendations-06nov13-en.htm. In addition, as required by the ICANN Bylaws, notification has been provided by the ICANN Board to the GAC (see http://www.icann.org/en/news/correspondence/crocker-to-dryden-12nov13-en). |
| Protection of Intergovernmental Organization Names in New gTLDs Staff: B. Cobb, M. Wong Chair: Thomas Rickert Council Liaison: Jeff Neuman | April 2012 | Nov 2013 | Board/Staff | The GNSO Council unanimously approved the motion on the IGO-INGO WG’s recommendations at its 20 Nov 2013 meeting. A public comment period has been opened until 18 Dec 2013 with a reply period set to close on 8 Jan 2014 as a requirement prior to the ICANN Board’s consideration of the consensus policy recommendations (http://www.icann.org/en/news/public-comment/igo-ingo-recommendations-27nov13-en.htm). Staff has also commenced work on the approved Issue Report relating to access by IGO/INGOs to curative protections such as the UDRP and URS procedures. |
| Issue Report on curative protections of the UDRP/URS for IGO/INGOs Staff: M. Wong, B. Cobb | 20 Nov 2013 | Jan 2013 | Staff | On the recommendation of the IGO-INGO PDP Working Group, the GNSO Council requested an Issue Report on exploring whether the curative rights of the UDRP and URS can be used by organizations that are granted based on their identified designations. |

| INACTIVE PROJECTS |
| --- |
| Uniform Dispute Resolution Policy Issue Report Staff: Request for an Issue Report on the current state of the UDRP. | 2011-Feb-03 | Completed for now (with further Issue Report due in March 2015) |  | The GNSO Council deferred commencement of a PDP, except with regard to the lock issue. An Issue Report reviewing all rights protection mechanisms (current and developed for the New gTLD Program) including the UDRP and URS was requested by the GNSO Council, to be delivered eighteen months after the first delegation of new gTLDS (which occurred in October 2013). |

| Joint SO/AC Working Groups |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Joint ccNSO-GNSO IDN Working Group (JIG) ccNSO Co-chair: Yound Eum Lee GNSO Co-chair: E. Chung Staff: B. Boswinkel, S. Sheng, M. Wong This group identified three IDN issues of common interest and is proposing ways to resolve them: 1) Single character IDN ccTLDs and gTLDs; 2) aspects of variant management in the root zone; and 3) universal acceptance of IDN TLDs. Both the ccNSO and GNSO have extended this charter to continue into 2012. | 2009 July-23 | Ongoing | WG/Council | Following are updates on each of the three key areas of work: Single Character IDN ccTLDs and gTLDs: The GNSO and ccNSO both approved a Final Report. In August the Board requested further advice from the SOs and ACs. New advice was offered by the SSAC, SAC 52, see, http://www.icann.org/en/committees/security/sac052.pdf. On 24 February, the GNSO and ccNSO Councils submitted a response to the Board reiterating support for the introduction of single character IDN TLDs and asking clarifying questions, see http://gnso.icann.org/mailing-lists/archives/council/msg12678.html. IDN Variant TLDs: The ICANN Board requested input from SOs and ACs in April 2013 (see http://www.icann.org/en/groups/board/documents/resolutions-11apr13-en.htm#2.a). The JIG has prepared a response letter which has now been approved by both the GNSO and ccNSO Councils and submitted to the Board. Universal acceptance. The JIG has published its Draft Final Report on this topic for public comment; reply comments which closed on 16 August 2013, http://www.icann.org/en/news/public-comment/idn-tld-acceptance-final-25jun13-en.htm). The JIG has finalized its report and forwarded it to the Council for approval (the ccNSO Council has already approved the report). |

| Approved GNSO PDP Recommendations - Status (For Information Only) |
| --- |
| Description | Adopted | Target Date | Who holds Token | Pending action/status |
| IRTP Part B PDP Adopted Recommendations |
| 5. Promotion by ALAC and other ICANN structures of the measures outlined in a recent SSAC report: A Registrant's Guide to Protecting Domain Name Registration Accounts (SAC 044). (See http://gnso.icann.org/resolutions/#201106 for text of resolution) | 22 June 2011 |  | SOs/ACs | Chair of the GNSO Council has sent messages to the Chairs of ALAC, SSAC, ccNSO, GAC, ASO (see http://gnso.icann.org/mailing-lists/archives/council/msg11736.html) to inform them about the recommendation and open discussions. |
| IRTP Part B Recommendation #9 – part 2 The GNSO Council resolved in Singapore that prior to consideration of the recommendation which states: "denial reason #7 should be replaced by adding a new provision in a different section of the IRTP on when and how domains may be locked or unlocked", the GNSO Council requests ICANN Staff to provide a proposal for such a new provision, taking into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report - (Recommendation #9 - part 2). Upon review of the proposal, the Council will consider the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation and staff proposal at its meeting in Costa Rica. ICANN Staff has started working on the implementation of the recommendation and expects to announce the implementation plan by the end of the year. |
| IRTP Part B Recommendation #8 The GNSO Council resolved in Singapore that prior to considering a recommendation to standardize and clarify WHOIS status messages regarding Registrar Lock status, the GNSO Council asked staff to provide a proposal to ensure that it is technically feasible to implement this recommendation. Staff should take into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report). (IRTP Part B Recommendation #8). The goal of these changes is to clarify why the Lock has been applied and how it can be changed. Upon review of the proposed plan, the Council will consider whether to approve the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation at its meeting on 6 May (see http://www.icann.org/en/groups/board/documents/resolutions-06may12-en.htm#1.5). ICANN Staff published the proposed implementation plan for public comment on 10 May 2013 (see http://www.icann.org/en/news/public-comment/wisp-10may13-en.htm). The Reply period for public comment closed on 24 June 2013. Staff expects to announce the implementation plan by the end of the year |
| IRTP Part C Recommendations |
| The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see http://gnso.icann.org/en/resolutions#20121017-4). | 17 Oct 2012 |  | Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December (see https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a). As instructed by the GNSO Council, an Implementation Review Team was formed and at its first meeting with staff the development of the implementation plan was discussed. Sessions will continue as necessary. |
| Locking of a Domain Name Subject to UDRP Proceedings Recommendations |
| The GNSO Council unanimously adopted the recommendations of the Locking of a Domain Name subect to UDRP Proceedings at its meeting of 1 August 2013. | 1 Aug 2013 |  | Staff | The ICANN Board adopted the Locking of a Domain Name subject to UDRP Proceedings at its meeting on 28 September (see http://www.icann.org/en/groups/board/documents/resolutions-28sep13-en.htm#1.c). As instructed by the GNSO Council, an Implementation Review Team has been formed. |

| Outstanding Recommendations for Council Action |
| --- |
| Description | Who holds Token | Pending action/status |
| None |