TABLE OF CONTENTS (click on the link below to go directly to the project in this list).

Projects are listed in the order in which they were initiated.

| GNSO Working Groups / Drafting Teams | Abbreviation |
| --- | --- |
| GNSO Improvements Standing Committee on Improvement Implementation | SCI |
| Drafting Team on Cross-Community Working Groups | CWG-DT |
| Fake Renewal Notices Drafting Team (To be removed in the next edition) | FRN-DT |
| Protection of Intergovernmental Organization Names in All gTLDs | IGO-INGO |
| IRTP Part D PDP Working Group | IRTP Part D |
| Policy & Implementation Working Group | PI |
| GNSO Metrics & Reporting WG (Uniformity of Reporting) | MetRep |

| Other GNSO Activities | Abbreviation |
| --- | --- |
| WHOIS Studies | WHO1 |
| RAA Privacy & Proxy Services Accreditation Issues | RAA |
| Defensive Registrations (To be removed in the next edition) | DefRg |
| Translation/Transliteration of Internationalized Registration Data |  |
| Purpose of Whois Issue Report | Whois PDP |
| Synthesis of WHOIS Service Requirements – Survey Working Group (Completed – to be removed in the next edition) | WHO2 |
| ‘Thick’ WHOIS PDP Working Group | Thick WHOIS |
| Uniform Dispute Resolution Policy (COMPLETED FOR NOW) | UDRP |

| Joint SO/AC Working Groups | Abbreviation |
| --- | --- |
| Geo Regions Review Community-wide Working Group | GEO |
| Joint ccNSO-GNSO Internationalized Domain Names Working Group (JIG) | JIG |
| Joint Security and Stability Analysis Community Drafting Group (DNS Cert) | DSSA |
| ccNSO Study Group on the Use of Names for Countries and Territories (Completed – to be removed in the next edition) | NCTSG |

| Approved GNSO PDP Recommendations | Abbreviation |
| --- | --- |
| IRTP Part B Adopted Recommendations | IRTP Part B |
| Inter-Registrar Transfer Policy Part C PDP | IRTP Part C |
| Locking of a domain name subject to UDRP proceedings | Lock |

| Outstanding Recommendations for Council Action | Abbreviation |
| --- | --- |

Last updated: 23 October 2013

This list includes pending GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| GNSO Working Groups / Work Teams / Drafting Teams |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| GNSO Standing Committee on Improvements Implementation (SCI) Chair: Ron Andruff Vice-Chair: Avri Doria Staff: J. Hedlund, M. Konings The GNSO Standing Committee on Improvement Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. | 2011-Apr-07 | Ongoing | SCI | The SCI is working on the following topics: Working Group survey; Re-submitting a motion. Voting by email. Waiver under the GNSO Operating Procedures. On 15 October the SCI sent a revised Charter to the Council Chair. The Council will consider the charter and decision-making methodology at its meeting on 31 October along with a motion to approve the revised charter. |
| Cross-Community Working Groups Framework Drafting Team Discussion leader: J. Robinson Staff: M. Wong, J. Hedlund A new CWG Framework drafting team will be formed to further refine the principles for cross-community working groups. | 19 May 2011 | Ongoing | Staff/J. Robinson | An initial set of draft principles was approved by the GNSO Council in March 2012, and feedback solicited from other SO/ACs. The ccNSO provided detailed comments and suggestions in June 2013. At its meeting on 10 October 2013, the GNSO Council passed a motion to establish a new CWG Framework Drafting Team that would include members from the other SOs and ACs, to be co-chaired by the GNSO and ccNSO. The new Drafting Team is to be formed by the time of the first GNSO Council meeting following the Buenos Aires meeting. The motion also called for staff to prepare a paper summarizing the original Drafting Team Principles and the feedback received from the ccNSO. |
| Fake Renewal Notices Drafting Team (FRN-DT) (To be removed n the next edition) Chair: Mikey O’Connor Staff: M. Konings The GNSO Council requested that a small group prepare a request for information concerning Fake Renewal Notices for the RrSG to help inform its deliberations on the RAP WG Recommendation on Fake Renewal Notices (#2). | 2011-Oct-06 | Ongoing | RrSG / Mason Cole | At its meeting in July, the GNSO Council considered the report of the Fake Renewal Notices DT (see http://gnso.icann.org/issues/frn/fake-renewal-notices-updated-report-20jun12-en.pdf). On the recommendation of the RrSG, a number of alternative approaches are now being pursued to address this issue, including working with ICANN Compliance, reaching out to the relevant local authorities and considering whether it would be appropriate to address this as part of the RAA negotations. The Council agreed to close this project at its meeting on 10 October, noting that no further GNSO work was foresoon on this issue in the near future. |
| Protection of Intergovernmental Organization Names in New gTLDs Staff: B. Cobb, M. Wong Chair: Thomas Rickert Council Liaison: Jeff Neuman | April 2012 | Nov 2013 | WG | The GNSO Council approved the motion to commence a PDP at the Toronto Meeting and adopted the WG Charter at its November 2012 meeting. The WG published its draft Final Report on 20 September. A public forum was opened on 20 September 2013, and will close on 31 October 2013. The WG is finalizing its proposed recommendations as it reviews the public comments received to date. The formal consensus call will be confirmed in preparation for the final report. The WG is targeting the Buenos Aires GNSO Council meeting to complete its efforts with submission of its Final Report by 10 November 2013. |
| IRTP Part D PDP WG Co-Chair: James Bladel, Mikey O’Connor Council Liaison: Volker Greimann Staff: L. Hoffmann, M. Konings. PDP on the remaining IRTP issues which include: Reporting requirements for registries and dispute providers in relation to the TDRP; How to handle disputes when multiple transfers have occurred in the TDRP; Should dispute options for registrants be developed; Should there be requirements or best practices for registrars to make information on transfer dispute resolution options available; Are existing penalties for policy violations sufficient; Have EPP AuthInfo codes eliminated the need for FOAs. | 17 Oct 2012 | Ongoing | WG | The WG held its first meeting on 25 February and will continue to meet on a weekly basis. The WG reached out to the community and has finished reviewing the received input. The WG is now in the process of drafting its initial recommendations and has agreed on draft recommendation for four of the six charter questions successfully so far. It will continue its substantive works focussing specifically on changes to the TDRP. The goal for the publication of the Initial Report is currently set for November 2013. |
| Policy & Implementation Working Group Co-Chairs: Chuck Gomes, J. Scott Evans Council Liaison: Jeff Neuman Staff: M. Konings, M. Wong The WG is tasked to provide the GNSO Council with a set of recommendations on: A set of principles that would underpin any GNSO policy and implementation related discussions A process for developing gTLD policy, perhaps in the form of “Policy Guidance”, including criteria for when it would be appropriate to use such a process (for developing policy other than “Consensus Policy”) instead of a GNSO Policy Development Process; A framework for implementation related discussions associated with GNSO Policy Recommendations; Criteria to be used to determine when an action should be addressed by a policy process and when it should be considered implementation, and; Further guidance on how GNSO Implementation Review Teams are expected to function and operate. | 9 May 2013 | Ongoing | WG | The Working Group held its inaugural meeting on Wednesday 21 August 2013. A sub-team has been formed to develop a work plan for the WG’s consideration. Following from the work plan sub-team’s initial work on mapping out the different activities, a second sub-team has now been formed to develop a set of working definitions that will inform the WG’s discussions and tasks as identified in the final work plan. |
| GNSO Metrics & Reporting DT (Uniformity of Reporting) Chair: M. O’Conner Staff: B. Cobb, L. Hoffmann The WG is tasked to provide the GNSO Council with a set of recommendations on: A set of principles that may compliment any GNSO policy efforts related to metric/data requirements to better inform the policy development process; A process for requesting metrics and reports both internal to ICANN or external, including GNSO contracted parties; A framework for distributing metrics and reports to Working Groups, the GNSO Council and the GNSO as a whole; Changes, if any, to existing Working Group Guidelines and work product templates | 17 Oct 2012 | On-going | DT | At its May 2013 meeting, the GNSO Council approved a motion to form a Drafting Team developing a charter for a non-PDP Working Group considering additional methods for collecting necessary metrics and reporting from Contracted Parties and other external resources. The WG is meeting weekly to complete the MetRep charter and submit it to the GNSO Council for their consideration at the Buenos Aires meeting in November. |

| Other GNSO Activities |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| STUDIES |
| WHOIS Studies Staff: Mary Wong The GNSO Council approved several studies of WHOIS. Topics include Misuse of WHOIS Data, Registrant Identification Information, Proxy and Privacy “Abuse” and Proxy and Privacy “Relay” and “Reveal”. Budget was approved by the ICANN Board for these studies. | 2007 Oct-31 | Ongoing | Staff | Staff is overseeing four studies of WHOIS as requested by the GNSO, the last of which are now nearing completion: A Misuse of Public gTLD WHOIS Data Study – conducted by researchers at Carnegie Mellon University (CMU). A draft of their initial findings has been just been completed and is undergoing review; current target for publication and public comment is late 2013. CMU will conduct a webinar during the public comment period. A Registrant Identification Study –launched in October 2011, with draft analysis by NORC. A webinar with summary findings was held on 6 March. The Final Report has been published. A Proxy/ Privacy “Abuse” Study – conducted by the National Physical Lab of the UK (NPL). The study was released for public comment on 24 September 2013. Staff will gather and review the public comments received with the NPL team, with a view to publishing a final report before the end of 2013. A pre-study “survey” on Proxy/Privacy “Relay” and “Reveal” – final report [PDF, 1.23MB] has been published and this study is now completed. |

| AWAITING COUNCIL ACTION |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| RAA Privacy & Proxy Services Accreditation Issues PDP Staff: M. Wong, M. Konings The Registrar Accreditation Agreement (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which have been identified as those relating to privacy & proxy services and their accreditation, will be examined in this PDP. | 2009 May-21 | Ongoing | Council | Staff published a paper outlining the background, current status and possible next steps related to commencing GNSO work on the PDP on 19 September 2013. Following from the Council’s meeting on 10 October, a draft charter was also prepared and circulated for Council discussion. The GNSO Council will consider a motion to adopt the draft charter, as further amended by Council discussions, at its meeting on 31 October 2013. |
| Translation/Transliteration of Internationalized Registration Data PDP. Staff: J. Hedlund/L. Hoffmann The Council approved the initiation of a PDP on translation and transliteration of contact information on 13 June 2013. | 17 Oct 2012 | 10 Oct 2013 | Council | The Drafting Team completed its work on the Charter, which has now been submitted to the GNSO Council for consideration. The motion to adopt the Charter was deferred to the 31 October meeting. If/when the Charter is adopted, a call for volunteers to form a Working Group will be circulated. |
| Defensive Registrations in New GTLDs: (To be removed in the next edition) The New GTLD Committee requests the GNSO to consider whether additional work on defensive registrations at the second level should be undertaken. | 4 June 2012 |  | Council | Staff has delivered a briefing paper http://gnso.icann.org/en/node/32287 and an update presentation to the GNSO Council on the topic of defensive registrations at the second level in response from a request from the New GLTD Committee (2012.04.10.NG2). The Council had an initial discussion on this item at its December meeting. The Council agreed to formally close this project at its last meeting, noting that no further GNSO work was foresoon on this issue in the near future. |

| Synthesis of WHOIS Service Requirements – Survey Working Group (Completed – to be removed in the next edition) Chair: Michael Young Staff: B. Cobb Council Liaison: Wendy Seltzer In May 2009 the GNSO Council asked staff to collect and organize a comprehensive list of potential WHOIS service requirements, based on current policies and previous policy discussions. See: http://gnso.icann.org/issues/whois/whois-service-requirements-final-report-29jul10-en.pdf This report was completed in 2010 and in May 2011 the GNSO Council created a WG to develop a survey to estimate the level of agreement that the conclusions and assumptions in the Inventory Report have in the community. | 2009 May-7 | 31-October | Staff | The WG closed the survey on 31 October 2012 with 67 complete submissions. ICANN Staff compiled and condensed the results by each survey section and produced a draft Final Report for WG review. The Working Group approved the Final Report and it was sent to the GNSO Council on 21 Aug 2013 for their consideration. The WSWG Recommendations were adopted by the GNSO Council at its 10 October meeting. Per the adopted resolution, the WSWG survey results will now be sent to the designated WHOIS efforts underway elsewhere in the community. |
| --- | --- | --- | --- | --- |
| ‘Thick’ WHOIS PDP WG Chairs: Mikey O’Connor Council Liaison: Volker Greimann Staff: M. Konings, B. Cobb As recommended by the IRTP Part B Working Group, the GNSO Council requested ICANN Staff to prepare an Issue Report on the requirement of ‘thick’ WHOIS for all incumbent gTLDs. At its meeting in Costa Rica, the GNSO Council initiated the PDP. | Nov 2012 | Ongoing | Council | Following its review of the public comments received, the WG delivered its Final Report to the GNSO Council on 21 October for the consideration at the 31 October GNSO Council meeting. |

| Staff Implementation |
| --- |
| Issue Report on the purpose of collecting and maintaining gTLD registration data and on solutions to improve accuracy and access to gTLD registration data. Staff: M. Wong, M. Konings, L. Hoffmann | 2012-Nov-8 |  | Staff | The Board resolution on the Whois RT Recommendations (see http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm) directs preparation of an Issue Report on the purpose of collecting and maintaining gTLD registration data, and on solutions to improve accuracy and access to gTLD registration data, as part of a Board-initiated GNSO policy development process. The Preliminary Issue Report was published for public comment on 15 March 2013. The comment forum closed on 13 May. A Final Issue Report will be published following the finalization of the EWG recommendations. |
| INACTIVE PROJECTS |
| Uniform Dispute Resolution Policy Issue Report Staff: Request for an Issue Report on the current state of the UDRP. | 2011-Feb-03 | Completed for now |  | The GNSO Council deferred commencement of a PDP, except with regard to the lock issue. An Issue Report was requested by the GNSO Council, to be delivered eighteen months after the first delegation of new gTLDS. |

| Joint SO/AC Working Groups |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Geo Regions Review Community-wide Working Group Chair: Dave Archbold (ccNSO) GNSO Council Reps: Zahid Jamil and Ching Chiao Staff: R. Hoggarth This Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions. Changes could have broad impact, so this WG has representatives from most SOs and ACs. | 2008 Aug-07 | 17 October 2013 | WG | The Working Group has published its Final Report recommendations (see - http://www.icann.org/en/news/announcements/announcement-22jun13-en.htm) The Final Report has been circulated to all ICANN SOs and ACs (including the Council) for review and comment. Comments (if any) were due to the Working Group on 17 October 2013). The Council did not submit comments to the WG. |
| Joint ccNSO-GNSO IDN Working Group (JIG) ccNSO Co-chair: Yound Eum Lee GNSO Co-chair: E. Chung Staff: B. Boswinkel, S. Sheng, M. Wong This group identified three IDN issues of common interest and is proposing ways to resolve them: 1) Single character IDN ccTLDs and gTLDs; 2) aspects of variant management in the root zone; and 3) universal acceptance of IDN TLDs. Both the ccNSO and GNSO have extended this charter to continue into 2012. | 2009 July-23 | Ongoing | WG/Council | Following are updates on each of the three key areas of work: Single Character IDN ccTLDs and gTLDs: The GNSO and ccNSO both approved a Final Report. In August the Board requested further advice from the SOs and ACs. New advice was offered by the SSAC, SAC 52, see, http://www.icann.org/en/committees/security/sac052.pdf. On 24 February, the GNSO and ccNSO Councils submitted a response to the Board reiterating support for the introduction of single character IDN TLDs and asking clarifying questions, see http://gnso.icann.org/mailing-lists/archives/council/msg12678.html. IDN Variant TLDs: The ICANN Board requested input from SOs and ACs in April 2013 (see http://www.icann.org/en/groups/board/documents/resolutions-11apr13-en.htm#2.a). The JIG has prepared a response letter which has now been approved by both the GNSO and ccNSO Councils and submitted to the Board. Universal acceptance. The JIG has published its Draft Final Report on this topic for public comment; reply comments which closed on 16 August 2013, http://www.icann.org/en/news/public-comment/idn-tld-acceptance-final-25jun13-en.htm). It is expected that the GNSO and ccNSO Councils will shortly consider next steps concerning the recommendations made by the JIG in its reports. |
| Joint Security and Stability Analysis Community Working Group (DNS Cert) ccNSO Co-Chair: Jörg Schweiger, .de GNSO Co-Chair: M. O’Connor Staff: B. Boswinkel, J. Hedlund | 2010 June | Ongoing | WG | The DSSA has provided a Phase I Draft Report to the Chartering SOs and ACs – including the GNSO. The DSSA-WG sent the Phase 1 Draft Report out for Public Comment through Toronto and will analyse comments received. The WG met in Durban and is preparing to submit its Final Phase 1 Report to its Chartering organizations and to ask them to consider whether and in what form this WG should continue to exist. |
| ccNSO Study Group on the Use of Names for Countries and Territories (ccNSO-NCTSG) (Completed – to be removed in the next edition) Chair: Paul Szyndler, .au Staff: B. Boswinkel This group of ccNSO, GNSO, GAC and ALAC representatives is considering policies and procedures to allocate TLD strings that are either associated with Countries and Territories (i.e. by inclusion in the ISO 3166-1 list) or are otherwise considered representations of Country or Territory names. | 8 Dec. 2010 | Ongoing | Study Group / Community | The focus of this project was on stocktaking current policy approaches, postulating the types and categories of strings that could be interpreted as country or territory representations and analysing what happens when policies are applied to the identified strings. The Final Report was submitted for consideration to the ccNSO Council. The ccNSO Council adopted the report and resolved to: Invite the ALAC, GAC and GNSO to establish a cross community working group, which is tasked to: Further review the current status of representations of country and territory names, as they exist under current ICANN policies, guidelines and procedures; Provide advice regarding the feasibility of developing a consistent and uniform definitional framework that could be applicable across the respective SO’s and AC’s; and Should such a framework be deemed feasible, provide detailed advice as to the content of the framework. The ccNSO secretariat is asked to coordinate drafting of a strawman for the charter of the proposed ccWG to facilitate the invitation and discussion with the SO’s and AC’s mentioned. |

| Approved GNSO PDP Recommendations - Status (For Information Only) |
| --- |
| Description | Adopted | Target Date | Who holds Token | Pending action/status |
| IRTP Part B PDP Adopted Recommendations |
| 5. Promotion by ALAC and other ICANN structures of the measures outlined in a recent SSAC report: A Registrant's Guide to Protecting Domain Name Registration Accounts (SAC 044). (See http://gnso.icann.org/resolutions/#201106 for text of resolution) | 22 June 2011 |  | SOs/ACs | Chair of the GNSO Council has sent messages to the Chairs of ALAC, SSAC, ccNSO, GAC, ASO (see http://gnso.icann.org/mailing-lists/archives/council/msg11736.html) to inform them about the recommendation and open discussions. |
| IRTP Part B Recommendation #9 – part 2 The GNSO Council resolved in Singapore that prior to consideration of the recommendation which states: "denial reason #7 should be replaced by adding a new provision in a different section of the IRTP on when and how domains may be locked or unlocked", the GNSO Council requests ICANN Staff to provide a proposal for such a new provision, taking into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report - (Recommendation #9 - part 2). Upon review of the proposal, the Council will consider the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation and staff proposal at its meeting in Costa Rica. ICANN Staff has started working on the implementation of the recommendation. |
| IRTP Part B Recommendation #8 The GNSO Council resolved in Singapore that prior to considering a recommendation to standardize and clarify WHOIS status messages regarding Registrar Lock status, the GNSO Council asked staff to provide a proposal to ensure that it is technically feasible to implement this recommendation. Staff should take into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report). (IRTP Part B Recommendation #8). The goal of these changes is to clarify why the Lock has been applied and how it can be changed. Upon review of the proposed plan, the Council will consider whether to approve the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation at its meeting on 6 May (see http://www.icann.org/en/groups/board/documents/resolutions-06may12-en.htm#1.5). ICANN Staff published the proposed implementation plan for public comment on 10 May 2013 (see http://www.icann.org/en/news/public-comment/wisp-10may13-en.htm). The Reply period for public comment closed on 24 June 2013. |
| IRTP Part C Recommendations |
| The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see http://gnso.icann.org/en/resolutions#20121017-4). | 17 Oct 2012 |  | Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December (see https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a). As instructed by the GNSO Council, an Implementation Review Team was formed and at its first meeting with staff the development of the implementation plan was discussed. Sessions will continue as necessary after the Durban meeting. |
| Locking of a Domain Name Subject to UDRP Proceedings Recommendations |
| The GNSO Council unanimously adopted the recommendations of the Locking of a Domain Name subect to UDRP Proceedings at its meeting of 1 August 2013. | 1 Aug 2013 |  | Staff | The ICANN Board adopted the Locking of a Domain Name subject to UDRP Proceedings at its meeting on 28 September (see http://www.icann.org/en/groups/board/documents/resolutions-28sep13-en.htm#1.c). As instructed by the GNSO Council, an Implementation Review Team will be formed. |

| Outstanding Recommendations for Council Action |
| --- |
| Description | Who holds Token | Pending action/status |
| None |