

| **Phase** | **Title** | **Links** |
| --- | --- | --- |
| **1 - Issue Identification** | **GNSO Council Action Items** [refer to list on wiki] | [LINK](https://community.icann.org/display/gnsocouncilmeetings/Action%2BItems) |
|  |  |  |
| **2 - Issue Scoping** | **Rights Protection Mechanisms in All gTLDs** (RPM) | [LINK](#UDRP) |
| **3 - Initiation** | **New gTLD Subsequent Rounds**  | [LINK](#subrnd_gTLD) |
| **4 - Working Group** | **Next-Generation gTLD Registration Directory Services (RDS) to replace WHOIS** (WHOIS PDP) | [LINK](#WHOIS_PDP) |
| **4 - Working Group** | **GNSO ICANN Meeting Strategy Drafting Team** | [LINK](#meeting) |
| **4 - Working Group** | **Cross Community Working Group on Enhancing ICANN Accountability** | [LINK](#CCWG) |
| **4 - Working Group** | **Curative Rights Protections for IGO/INGOs** (IGO-INGO-CRP) | [LINK](#IGO_INGO_RPM) |
| **4 - Working Group** | **GNSO Standing Committee on Improvements Implementation** (SCI) | [LINK](#SCI) |
| **4 - Working Group** | **Privacy & Proxy Services Accreditation Issues Working Group** (PPSAI) | [LINK](#PPSAI) |
| **4 - Working Group** | **GNSO PDP Improvements Discussion Group** (PDP-IMPR) | [LINK](#PDP_IMPR) |
| **4 - Working Group** | **GNSO Review Working Party** (REVIEW) | [LINK](#REVIEW) |
| **4 - Working Group** | **Geo Regions Review Community-wide Working Group** (GEO) | [LINK](#GEO) |
| **4 - Working Group** | **GAC-GNSO Consultation Group on Early Engagement** (GAC-GNSO-CG) | [LINK](#GAC_GNSO_CG) |
| **4 - Working Group** | **Cross-Community Working Group to develop a Framework of Principles for Future CWGs** (CWG-Principles) | [LINK](#CWG_CWG) |
| **4 - Working Group** | **Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs** (CWG-UCTN) | [LINK](#CWG_UTCN) |
| **4 - Working Group** | **Cross-Community Working Group on Internet Governance** (CWG-IG) | [LINK](#IG) |
| **5 – Council Deliberations** | **-none-** | -none- |
| **6 – Board Vote** | **Protection of International Organization Names in All gTLDs PDP** (IGO-INGO) | [LINK](#IGO_INGO) |
| **7 – Implementation** | **GNSO Data & Metrics for Policy Making Working Group** (DMPM) | [LINK](#DMPM) |
| **7 – Implementation** | **Policy & Implementation Working Group** (POLIMP) | [LINK](#POLIMP) |
| **7 – Implementation** | **Translation/Transliteration of Internationalized Registration Data Working Group** (T&T) | [LINK](#TandT) |
| **7 – Implementation** | **Inter-Registrar Transfer Policy Part B PDP** (IRTP-B) | [LINK](#IRTP_B) |
| **7 – Implementation** | **Inter-Registrar Transfer Policy Part C PDP** (IRTP-C) | [LINK](#IRTP_C) |
| **7 – Implementation** | **‘Thick’ WHOIS PDP** (THICK-WHOIS) | [LINK](#THICK_WHOIS) |
| **7 – Implementation** | **Protection of International Organization Names in All gTLDs PDP** (IGO-INGO) | [LINK](#IGO_INGO2) |
| **7 – Implementation**  | **IRTP Part D PDP Working Group** (IRTP-D) | [LINK](#IRTP_D) |
| **7 – Implementation** | **Cross Community Working Group to Develop an IANA Stewardship Transition Proposal on Naming Related Functions** | [LINK](#IANA) |
| **Other** | **-none-** | -none- |

Last updated: 8 December 2015

This list includes GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| **1 - Issue Identification** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| GNSO Council Action Items - [LINK](https://community.icann.org/display/gnsocouncilmeetings/Action%2BItems) | NA | NA | NA | Refer to action list for latest status |

| **2 - Issue Scoping** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
|  |  |  |  |  |
| **Rights Protection Mechanisms in All gTLDs Issue Report** Staff: M. Wong. L. Hoffmann | 2011-Feb-03 | ongoing | Staff | The public comment period for the [Preliminary Issue Report](http://gnso.icann.org/en/issues/new-gtlds/rpm-prelim-issue-09oct15-en.pdf) on a potential GNSO PDP to review all rights protection mechanisms (RPMs) in all gTLDs closed on 30 November 2015 and 22 submissions were made. Staff completed the public comment summary on 2 December and is now updating the Issue Report to be submitted to the GNSO Council in due course.  |

| **3 – Initiation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **New gTLD Subsequent Procedures**Staff: S. Chan, J. HedlundThe GNSO Council requested a Preliminary Issue Report on new gTLD subsequent procedures during its meeting on 25 June 2015.  | 2014-Jun-25 | 2015-Dec | Council | Based primarily on the work of the new gTLD Subsequent Procedures Discussion Group, the GNSO requested a Preliminary Issue Report on New gTLD Subsequent Procedures at its meeting on 25 June 2015. The Preliminary Issue Report was completed and published for public comment (<https://www.icann.org/public-comments/new-gtld-subsequent-prelim-2015-08-31-en>) on 31 August 2015 with a close date of 30 October 2015. Incorporating the feedback from a public session on the Preliminary Issue Report at ICANN 54 in Dublin and public comments received, staff submitted the Final Issue Report to the GNSO Council on 4 December. The GNSO Council will now consider whether to initiate a PDP during its 17 December meeting. |
|  |  |  |  |  |

| **4 – Working Group** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **Issue Report on the next generation gTLD Registration Directory Service to replace WHOIS**Chair(s): TBC[Council liaison](https://community.icann.org/x/9SnxAg): Susan Kawaguchi, Chair Staff: M. Konings | 2012-Nov-8 | Ongoing | Staff | The ICANN Board reconfirmed its request for a Board-initiated GNSO PDP to define the purpose of collecting, maintaining and providing access to gTLD registration data, and consider safeguards for protecting data, using the recommendations in the EWG [Final Report](https://www.icann.org/en/system/files/files/final-report-06jun14-en.pdf) as an input to, and, if appropriate, as the foundation for a new gTLD policy. The Preliminary Issue Report was published for public comment on 13 July, with the comment period closing on 6 September (see <https://www.icann.org/public-comments/rds-prelim-issue-2015-07-13-en>). The Final Issue Report was sent to the GNSO Council on 7 October (see <http://whois.icann.org/sites/default/files/files/final-issue-report-next-generation-rds-07oct15-en.pdf>), while the charter for the PDP WG was adopted during the Council’s meeting on 19 November. A call for volunteers to form the PDP WG will be launced by 4 January 2016. |
| **GNSO ICANN Meeting Strategy Drafting Team**Council Lead:Volker GreimannStaff support: M. Konings, G. de Saint-Gery | 2015-Feb-11 | ICANN54 | DT | The GNSO Council agreed during its meeting in Singapore to form a drafting team to develop a proposed framework for GNSO related meetings as part of the new ICANN meeting strategy which will go into effect in 2016. The DT developed a draft proposed approach which was shared with other SO/ACs for discussion in Buenos Aires. Following that meeting [a letter](http://gnso.icann.org/en/correspondence/robinson-to-crocker-14jul15-en.pdf) was sent by Jonathan Robinson on behalf of the GNSO Council to inform the ICANN Board of the progress to date and to request the ICANN Board to share further information concerning its plans. Some further discussions between the different SO/ACs took place during the ICANN meeting in Dublin (see also <https://community.icann.org/x/_o5Caw>) and are expected to continue prior to the Marrakech meeting.  |
| **[Cross Community Working Group on Enhancing ICANN Accountability](https://community.icann.org/x/ogDxAg)**Co-Chairs: Mathieu Weill (ccNSO), Thomas Rickert (GNSO), Leon Sanchez (ALAC)Staff support: G. Abuhamad, A. Jansen | 2014-Oct-16 | Ongoing | CCWG | The GNSO Council approved the CCWG [Charter](http://gnso.icann.org/en/council/resolutions#20141113-1) at its November 2014 meeting. The charter has been approved to date by the ccNSO, GAC and ALAC, in addition to the GNSO. The CCWG has a near-term focus of collecting current and possible future accountability mechanisms to be assigned in Work Streams 1 & 2, with WS1 being considered the more urgent accountability mechanisms required for the IANA Stewardship transition to take place. The CCWG has formed three Work Parties to further develop Community Powers, Accountability Mechanisms, and Stress Tests. Legal advisors were engaged to assist the CCWG as well. After review of the public comments on the first version of the WS1 proposal, face to face sessions at ICANN53 and a subsequent face to face meeting in Paris, the CCWG launched a [second public comment period](https://www.icann.org/public-comments/ccwg-accountability-2015-08-03-en) based on the proposed single member community mechanism on 3 Aug 2015. The public comment period closed on 12 Sept 2015. Additionally, the ICANN Board submitted its comments regarding a multi-stakeholder model for the CCWG to consider. The CCWG held several sessions in Dublin. The CCWG co-chairs issued a preliminary summary on 15 November and the full Third Draft Proposal was published on 30 November, with public comments closing on 21 December. SO/AC Chartering Organizations have been requested to consider whether to approve the proposal as early as possible, and the GNSO Council has scheduled an additional meeting in January 2016 to continue discussions from its 17 December meeting, if needed.  |
| **[Curative Rights Protections for IGO/INGOs](http://community.icann.org/display/gnsoicrpmpdp/)**Chair: Philip Corwin, Petter Rindforth Council Liaison: Susan KawaguchiStaff: M. Wong, S. ChanThe PDP WG is tasked to explore possible amendments to the Uniform Dispute Resolution Policy (UDRP) and the Uniform Rapid Suspension procedure (URS) so as to enable International Governmental Organizations (IGOs) and International Non-Governmental Organizations (INGOs) to access and use curative rights protection mechanisms | 2014-Jun-05 | Ongoing | WG | Based on the recommendation of the IGO-INGO PDP Working Group, the GNSO Council resolved to initiate a PDP and chartered a WG in June 2014. The WG has made considerable progress in its Work Plan and is focusing its attention on IGOs, as it has preliminarily determined that INGOs do not appear to require additional protections. The WG has reached a preliminary conclusion on the issue of standing and is currently discussing jurisdictional immunity for IGOs within the construct of rights protection mechanisms. It has decided to procure the services of an external legal expert on this topic, selecting Professor Edward Swaine from George Washington University to perform the work. A contract has been signed by ICANN with Professor Swaine, who is expected to provide his opinion within the next few weeks.A follow up set of questions was sent to the IGOs on the issue of IGO immunity as well. The WG is currently also anticipating the delivery of a proposal from the small group of NGPC, GAC and IGO representatives that was formed on the topic. It expects to conduct further engagement with the GAC and IGOs upon receipt of the proposal. An open WG meeting was held in Dublin on Thursday morning. |
| **[GNSO Standing Committee on Improvements Implementation (SCI)](https://community.icann.org/display/gnsosci/Home)**Chair: Anne Aikman-ScaleseVice-Chair: Rudi VansnickCouncil Liaison: Avri DoriaStaff: J. Hedlund, M. Wong, M. Konings The GNSO Standing Committee on Improvements Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. It is a standing committee of the GNSO Council. | 2011-Apr-07 | Ongoing | SCI | In April the GNSO Council consented to referring two issue requests to the SCI for consideration. The [first](https://community.icann.org/display/gnsocouncilmeetings/Motions%2B16%2BApril%2B2015) concerned GNSO Council practices for proposing, seconding, and amending motions and the [second](https://community.icann.org/display/gnsocouncilmeetings/Motions%2B16%2BApril%2B2015) concerned the clarifying of the GNSO Operating Procedures regarding the waiver and resubmission of motions. The SCI has reached consensus that the GNSO Operating Procedures are clear that the waiver of the 10-day deadline for motions does not apply to resubmitted motions and sent a letter to Jonathan Robinson on 09 October notifying the GNSO Council of its decision. The SCI has also documented the Council’s current practice in relation to motions (include amendments) and sent a letter on 09 October with the documented practice to Jonathan Robinson for the GNSO Council to review in Dublin. This was the first step in the Review Request for that issue. The second step will be for the SCI to discuss whether and/or how the GNSO Operating Procedures might be changed. The SCI held a face-to-face meeting at ICANN 54 in Dublin and provided an update to the Council. At its 19 November meeting the GNSO Council approved a motion to asking the SCI to review Sections 2.2(f) and 2.2(g) of the GNSO Operating Procedures (GNSO Council Vice-Chairs serving as interim GNSO Chairs, and posting of GNSO Chair election results). The SCI will begin consideration of this new request at its next meeting on 10 December. |
| **[Privacy & Proxy Services Accreditation Issues PDP WG](https://community.icann.org/pages/viewpage.action?pageId=43983094)** Chair: Don BlumenthalVice-Chairs: Graeme Bunton, Steve MetalitzCouncil Liaison: James BladelStaff: M. Wong, M. Konings The *Registrar Accreditation Agreement* (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which have been identified as those relating to privacy & proxy services and their accreditation, will be examined in this PDP. | 2009-May-21 | Ongoing | WG | The WG’s Initial Report was published for public comment on 5 May: see <https://www.icann.org/public-comments/ppsai-initial-2015-05-05-en>, and closed on 7 July. Following a community session in Buenos Aires to discuss the Initial Report, the WG began its review of all public comments received. Due to the volume of comments, the WG created four Sub Teams to facilitate review of the comments, and revised its timeline for completion of its Final Report. It held a face to face meeting at ICANN54 and is in the final stages of a consensus call on its Final Report, which it hopes to submit to the GNSO Council in time for the Council’s 17 December meeting. |
| **GNSO PDP Improvements Implementation Discussion Group**Volunteers: Dan ReedStaff: M. Konings, Lars HoffmannThe GNSO Council agreed to form a small committee of interested Council members to work with staff on the implementation of the GNSO PDP Improvements (see <http://gnso.icann.org/en/drafts/pdp-improvements-table-16jan14-en.pdf>), particularly items 3 (Increase pool of PDP volunteers) and 5 (Improved online tools & training) . | 2014-Jan-30 | Ongoing | Council /Staff | The group has been dormant awaiting the development of further initiatives and assessment of further need for consultation by staff.Staff provided a status update on the implementation of the recommendations during the ICANN meeting in Buenos Aires and will continue to move forward with the implementation of the previously identified GNSO PDP improvements, incorporating the suggestions made.Following very helpful feedback from the Community, Staff completed the GNSO Learn module and presented it to the GNSO in Dublin. The [course is live](http://learn.icann.org/courses/gnso) and a social media campaign to promote has launched in late November. |
| **[GNSO Review Working Party](https://community.icann.org/x/OJLhAg)**Lead: Jennifer WolfeStaff: M. Konings, M. WongFollowing discussions in Singapore, the GNSO Council agreed to form a small committee to liaise with the Board’s Structural Improvements Committee (now the Organizational Effectiveness Committee (OEC)) on the GNSO Review and discuss a potential self-review of the GNSO Council. | 2014-Apr-07 | Ongoing | Working Party | Westlake, the independent examiner selected by the SIC , shared its draft Workng Text with the GNSO Review Working Party after ICANN52 and met with the Working Party to discuss its and SG/C feedback received. As a result of the feedback and discussions, the timeline was extended to allow Westlake to fully consider and incorporate corrections and suggestions from the community. A Draft Report was delivered to the Working Party in late April, and two meetings with the Working Party were held to receive and review input. The Initial Report was published for public comment on 1 June, with the comment period closing on 24 July: <https://www.icann.org/public-comments/gnso-review-draft-2015-06-01-en>. A final report was published on 15 September: see <https://www.icann.org/news/announcement-2-2015-09-15-en>. The GNSO Review Working Party has met to discuss the final report, and plans to submit feedback to the Board’s OEC. It is finalizing its feedback on the final report and is discussing issues relating to implementability of the recommendations. |
| **[Geo Regions Review Community-wide Working Group](https://community.icann.org/display/georegionwg/Home%2BPage%2Bof%2BGeographic%2BRegions%2BReview%2BWorking%2BGroup)**Chair: Cheryl Langdon-Orr (ccNSO)GNSO Council Reps: Staff: R. HoggarthThis Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions. Changes could have broad impact, so this WG has representatives from most SOs and ACs. | 2008-Aug-07 | April 2016 | Board | The Working Group submitted its Final Report recommendations to the ICANN Board on 4 November 2015. The next anticipated step is for the Board to direct staff to open a public comment period to review the WG recommendations. It is likely that community comments will be accepted up to and after the ICANN Public Meeting in Marrakech. |
| **[GAC-GNSO Consultation Group on GAC Early Engagement in GNSO PDP](https://community.icann.org/x/phPRAg)**Chairs: Jonathan Robinson (GNSO) and Manal Ismail (GAC)Staff: M. Konings, O. NordlingThe Governmental Advisory Committee (GAC) and the Generic Names Supporting Organization (GNSO) have jointly established a consultation group to explore ways for the GAC to engage early in the GNSO Policy Development Process (PDP) and to improve overall cooperation between the two bodies (for example, by exploring the option of a liaison). | 2014-Jan-07 | Ongoing | CG | The launch of this GAC-GNSO Consultation Group on Early Engagement is the result of discussions between the two entities at the ICANN meeting in Buenos Aires as well as previous ICANN meetings, reflecting a joint desire to explore and enhance ways of early engagement in relation to GNSO policy development activities. The issue was also specifically called-out by both Accountability and Transparency Review Teams (ATRT). The CG reconvened following the ICANN meeting in Dublin and has commenced working on the review of the GNSO Liaison to the GAC, the review of the Quick Look Mechanism as well as identifying other opportunities for early engagement of the GAC in the GNSO PDP.  |
| **[Cross-Community Working Group- on a Framework of CWG Principles](https://community.icann.org/x/rQbPAQ)**GNSO Council Co-Chair: John BerardccNSO Council Co-Chair: Becky BurrStaff: M. Wong, B. Boswinkel, S. ChanThe CWG was chartered by the ccNSO and GNSO Councils to further refine the principles initially drafted by the GNSO and commented on by the ccNSO for the formation, operation and termination of future cross-community working groups. | 2011-May-19 | Ongoing | CWG | This Cross-Community Working Group was chartered by both the ccNSO and GNSO Councils in March 2014. The CWG has reviewed the processes and outcomes of selected prior CWGs, including mapping their charters to the typical WG life cycle (Initiation of CWG, Formation, Operation, Closure, Post-Closure). As a result of the recent further usage of new CWGs, the co-chairs and staff prepared a preliminary draft checklist for all the various stages of the WG life cycle, which was shared with the community at the Buenos Aires meeting. A revised draft framework is being prepared by staff. Following approval by the CWG, the proposed framework will be circulated to the Chartering Organizations and published for public comment before ICANN55. |
| **[Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs (CWG-UCTN)](https://community.icann.org/x/X7XhAg)**GNSO Council Co-Chairs: Heather Forrest, Carlos Gutierrez ccNSO Council Co-Chairs: Paul Szyndler, Annabeth LangeCouncil liaison: Heather ForrestStaff: M. Konings, B. Boswinkel, Lars Hoffmann* The objective of the CWG is to: Further review the current status of representations of country and territory names, as they exist under current ICANN policies, guidelines and procedures;
* Provide advice regarding the feasibility of developing a consistent and uniform definitional framework that could be applicable across the respective SO’s and AC’s; and
* Should such a framework be deemed feasible, provide detailed advice as to the content of the framework.
 | 2014-Mar-26 | Ongoing | CWG | The CWG is using a straw man Options Paper to drive forward its discussion and has just concluded its work on two-letter codes. The Group is now discussing 3-letter codes and has sent out a request for input to all SO/ACs and SG/Cs – over thirty responses have come back and the Group has started its discussion on this complex issue. Communication channels with the GAC remain upon regarding potentially overlapping work efforts.  |
| **[Cross-Community Working Group on Internet Governance (CCWG-IG)](https://community.icann.org/pages/viewpage.action?pageId=43984275)**Co-Chairs: Rafik Damak (GNSO), Jordan Carter (ccNSO), Olivier Crepin-Leblond (ALAC)GNSO Council Liaison: Carlos GutierrezStaff: A-R Inne, N. Hickson, R. DewulfThe Internet Governance CWG has been established by the participating SO’s and AC’s to coordinate, facilitate, and increase the participation of the ICANN community in discussions and processes pertaining to Internet Governance.  | 2014-Oct-15 | Ongoing | CCWG | The GNSO Council adopted the charter for this CCWG during ICANN51. The CCWG [held](file://C:\..\user\AppData\Local\Microsoft\Windows\Temporary%20Internet%20Files\Content.Outlook\AppData\Local\Microsoft\Windows\Temporary%20Internet%20Files\Library\Caches\TemporaryItems\AppData\Local\Microsoft\Windows\Temporary%20Internet%20Files\Library\Caches\TemporaryItems\Library\Library\Library\Caches\TemporaryItems\AppData\Local\Microsoft\Windows\Temporary%20Internet%20Files\Library\Caches\Library\Library\Caches\TemporaryItems\AppData\Local\Microsoft\Windows\Temporary%20Internet%20Files\Library\Caches\Library\Library\Caches\TemporaryItems\Users\Berry\AppData\Local\Microsoft\Windows\INetCache\Content.Outlook\Library\Library\Caches\Library\Library\Caches\Library\Caches\TemporaryItems\Library\Library\Caches\Library\Caches\Library\Caches\TemporaryItems\Outlook%20Temp\held) a community session at ICANN53. It requested confirmation from its Chartering Organizations regarding a question of interpretation of its charter, which the GNSO Council agreed to at its May 2015 meeting. |

| **5 – Council Deliberation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **-none-** |  |  |  |  |

| **6 – Board Vote** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[Protection of International Organization Names in All gTLDs](http://gnso.icann.org/en/group-activities/active/igo-ingo)**Staff**:** M. WongChair**:** Thomas RickertCouncil Liaison**:** Thomas Rickert | 2012-Apr-12 | 2014-Dec-11 | Board/Council | The GNSO Council unanimously approved the IGO-INGO WG’s consensus recommendations at its 20 Nov 2013 meeting. As requested by the Board, the NGPC developed a proposal taking into account the GNSO’s recommendations and GAC advice in March 2014. In April 2014 the Board voted to adopt those of the GNSO’s recommendations that are not inconsistent with GAC advice received on the topic. Staff has organized an Implementation Review Team (in line with the GNSO’s recommendation), led by Fabien Betremieux, to implement those recommendations adopted by the Board (See below in the “7 – Implementation” section for more details). A Call for Volunteers to the IRT was issued following the Buenos Aires meeting and the IRT held its first meeting in late September. It plans to meet again in Dublin.On 18 June 2014 the NGPC sent a letter to the GNSO Council requesting that the GNSO contemplate initiating a process to consider possible modifications to its remaining recommendations, per the PDP Manual. The GNSO Council held a discussion with Chris Disspain at its 5 September meeting and sent a [letter](http://gnso.icann.org/en/correspondence/robinson-to-chalaby-disspain-07oct14-en.pdf) on 7 Oct 2014 to the NGPC seeking confirmation and input about the most appropriate forms of protection for IGO acronyms and Red Cross names. At the ICANN51 meeting the NGPC adopted a resolution to temporarily reserve the Red Cross National Society identifiers until the differences between the GNSO recommendations and the GAC Advice have been reconciled. Staff is currently working on implementing this resolution, with assistance from the Red Cross. A response from the NGPC to the Council’s letter was received on 15 January 2015 noting that discussions are ongoing. The Council is likely to await further and more definite information from the NGPC before taking any further action on this point. An updated proposal from a small group of IGO, GAC and NGPC representatives is expected to be delivered to the GNSO for consideration following ICANN54. |

| **7 – Implementation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[GNSO Data & Metrics for Policy Making WG](https://community.icann.org/display/marwg) (DMPM)**Staff**:** S. Chan, L. HoffmannThe Data & Metrics for Policy Making Working Group (WG) explored opportunities to review standard methodologies of reporting and metrics that could better inform fact-based policy development and decision making; including how the community can collaborate with Contracted Parties and other service providers in the sharing of metrics and data. | 2012-Oct-17 | Ongoing | Staff | The DMPM completed its Final Report and submitted it to the GNSO Council for its consideration at the Dublin meeting. The recommendations were unanimously adopted. Staff is now implementing the WG’s recommendations. Work product templates are in the review stage prior to publication and the GNSO Operating Procedures will be updated shortly after that. |
| **[Policy & Implementation](https://community.icann.org/pages/viewpage.action?pageId=41899467)** | 2013-May-09 | Ongoing | Staff | The Council voted to adopt the Policy & Implementation [Final Report](http://gnso.icann.org/en/issues/policy-implementation/pi-wg-final-recommendations-01jun15-en.pdf) and its recommendations during its public meeting in Buenos Aires. At its last meeting on 28 September, the Board approved the proposed Bylaw changes associated with the recommendations. Implementation of the changes to the necessary Bylaws and GNSO procedures is underway. |
| **[Translation/Transliteration of Internationalized Registration Data PDP](https://community.icann.org/display/tatcipdp/Translation%2Band%2BTransliteration%2Bof%2BContact%2BInformation%2BPDP%2BHome)**  | 2012-Oct-17 | Ongoing | Staff | On 28 September the ICANN Board [passed the motion](https://www.icann.org/resources/board-material/resolutions-2015-09-28-en) to adopt all seven recommendations contained in the Final Report. GDD Staff will is currently working on the Implementation Review plan, a call for volunteers to joining the Implementation Review Team is forthcoming. |
|  |  |  |  |  |
| **IRTP Part C Recommendations** The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see <http://gnso.icann.org/en/resolutions#20121017-4>).  | 17 Oct 2012 | 1 Sept 2015 | Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December 2012 (see <https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a>). As instructed by the GNSO Council, an Implementation Review Team was formed. Meetings of the IRT have recommenced and details of the proposed implementation plan have been shared with the IRT. Staff sought input from the IRT on the Change of Registrant draft policy language, and the draft policy was posted for public comment on 30 March 2015. Comments were due 16 May 2015, and the IRT reviewed the comments received. The updated Transfer Policy was announced on 24 September 2015 (see <https://www.icann.org/news/announcement-2-2015-09-24-en>). The updated Transfer Policy will be effective for all ICANN-accredited registrars 1 August 2016. |
| **Thick WHOIS PDP Recommendations**The GNSO Council adopted the recommendation to require Thick Whois for all gTLD registries at its meeting on 31 October 2013.  | 2012-Mar-14 | Ongoing | Staff | The ICANN Board approved the GNSO recommendations on Thick Whois at its meeting on 7 February 2014. (<http://www.icann.org/en/groups/board/documents/resolutions-07feb14-en.htm>). An Implementation Review Team has been formed and various impact assessments and implementation proposals have been discussed with the IRT in the two decoupled work streams, corresponding to the two expected outcomes in the PDP Recommendations: transition from thin to thick for .COM, .NET and .JOBS; and the consistent labeling and display of Whois output for all gTLDs as per Specification 3 of the 2013 RAA. Further discussions of the proposals, issues, and risks are being planned in subsequent IRT sessions. Regarding the transition from thin to thick for .COM, .NET and .JOBS, in June 2015, ICANN’s General Counsel’s Office, released to the IRT a Legal Review Memorandum per the GNSO Council’s recommendation. ICANN Staff is currently engaging with experts from affected parties on draft implementation proposals to address data transfer restrictions and potential conflicts with local laws.Regarding the Consistent Labeling and Display of Whois output for all gTLDs, ICANN Staff, in conjunction with the IRT have been working together to develop a Draft Consensus Policy on wich Community input will soon be sought. |
| **Protection of International Organization Names in All gTLDs** The GNSO Council adopted the recommendation to protect certain identifiers of IGO & INGO Organizations in all gTLD registries at its meeting on 20 November 2013. | 2012-Apr-12 | Ongoing | Staff | The GNSO Council unanimously approved the IGO-INGO WG’s consensus recommendations at its 20 Nov 2013 meeting. In April 2014 the Board voted to adopt those of the GNSO’s recommendations that are not inconsistent with GAC advice received on the topic. Staff has formed an Implementation Review Team (in line with the GNSO’s recommendation), led by Fabien Betremieux, to implement those recommendations adopted by the Board.A call for IRT volunteers was issued after the ICANN 53 meeting and the first meeting held in September. The IRT also met at ICANN54. To date, ICANN Staff has been working on building comprehensive and actionable lists of all the identifiers to be protected as well as draft procedures for eventual implementation of relevant protections: reservations at the top and second levels and related exception procedures. A Draft Consensus Policy Outline has been circulated to the IRT and will serve to support the continuing development of the implementation plan. |
| [**IRTP Part D PDP WG**](https://community.icann.org/display/ITPIPDWG/Inter-Registrar%2BTransfer%2BPolicy%2B%28IRTP%29%2BPart%2BD%2BWorking%2BGroup%2BHome)* The GNSO Council unanimously adopted the recommendations of the IRTP Part D PDP at its meeting on 15 October 2014 (see http://gnso.icann.org/en/council/resolutions#20141015-1).
 | 2012-Oct-17 | Ongoing | Staff | The ICANN Board approved the GNSO recommendations of IRTP D on 12 February 2015 (https://www.icann.org/resources/board-material/resolutions-2015-02-12-en#1.d). GDD staff has drafted an Implementation Plan and the Implementation Review Team (IRT) has been meeting on a biweekly basis since August. The draft Transfer Dispute Resolution Policy and draft Transfer Policy were posted for public comment on 10 November 2015. The comment period closes 21 December 2015.  |
| **[Cross Community Working Group to Develop an IANA Stewardship Transfer Proposal on naming related functions](https://community.icann.org/display/gnsocwgdtstwrdshp/CWG%2BDrafting%2BTeam%2Bon%2BStewardship%2BTransition%2BHome)**Co-Chairs: Jonathan Robinson (GNSO), Lise Fuhr (ccNSO)Council Liaison: Jonathan RobinsonStaff: M. Konings, B. Boswinkel, G. AbuhamadThis CWG has been formed to develop an IANA Stewardship Transfer Proposal on naming related functions. | 2014-Jul-14  | Ongoing | ICG/CWG | The CWG delivered the final proposal for SO/AC consideration on 11 June. The GNSO Council, in addition to all other chartering organization approved the CWG’s names proposal during the ICANN 53 meeting in Buenos Aires. As a result, the CWG submitted the names related proposal to the ICG. The ICG has published the proposal to transition the stewardship of the IANA functions, which integrates the proposals of all three operational communities, for public comment from July 31 to September 8 (see https://www.ianacg.org/calls-for-input/combined-proposal-public-comment-period/). The CWG will await the outcomes of the CCWG given the documented dependencies related to any changes to ICANN’s accountability framework and is continuing to meet every two weeks to address issues in relation to the implementation of the IPR and budget recommendations. The CWG-Stewardship most recently contacted all the chartering organizations, including the GNSO, to confirm whether there are any objections to the CWG-Stewardship continuing its role to work with staff in relation to implementation. No objections have been received to date. |