ccNSO activity overview (work plan)

Monthly update

Version: September 2013

| Overview ccNSO policy (related) activities version May 2013 |
| --- |
| Activity | Description | Initiated | Target Date | Chair/ owner | Pending action/status dependency |
| Framework of Interpretation WG | Consent |  |  | Keith Davidson | To be included in full set of recommendations |
|  | SIP |  | Beijing (11 April) | Keith Davidson | GAC Response received June 2012. FoI WG send response October 2012. Awaiting further comments from GAC before finalizing Report on SIP. No progress to date |
|  | Revocation |  | Closure at Singapore meeting | Keith Davidson | Discussion at WG level in preparation of Interim Report concluded. Interim report to be published before Buenos Aires meeting. |
|  | IANA Reporting |  |  | Keith Davidson |  |
|  | Glossary |  |  | Keith Davidson |  |
|  | Closing report |  |  | Keith Davidson | Closure of the FoI WG. Depends on Finalisation of Final report |
| IDN ccPDP | Overall Policy selection IDN ccPDP Final Report | 18 October 2012 | 8 Nov. 2012 | Chris Disspain | Final report published December 2012 |
|  | Inclusion IDN ccTLD in ccNSO Final Report |  | 8 Nov. 2012 | Hiro Hotta | Final report adopted by WG and published. To be included in Interim report |
|  | Interim Report ccPDP | 1 December 2012 Publshed 5 February 2013 | 21 February 2013 Closing date end March 2013 | Issue Manager | Completed |
|  | Final Report ccPDP |  | 15 Feb 2013 | Issue Manager | Completed |
|  | Council Vote | Submit Final Report 29 March 2013, Inform the GAC chair | Council Beijing 10 April 2013 | Chair of the ccNSO | Final Report adopted Completed |
|  | Members Vote | Announce 11 April | 27 June | ccNSO Council | Members report, including the deliberations and outcome of Council vote published. Webinar on Council Recommendation and voting process 15 May Voting opens 23 May 2013. Potential issue: at least 50% of members need to vote (68 or more members of the ccNSO) Risk with regard to lack of voters seems to materialize. If happens the Members will be noticed and 30 days after the notice a second, final round will be conducted. |
|  | Board Report. To be adopted by Council |  | 23 August 2013 | ccNSO Council | Outcome ccNSO Members vote. Completed and adopted |
|  | Submit Board paper |  |  | Issue Manager | Awaiting clarification porcess |
| Retirement of ccTLD PDP |  | To be determined |  |  |  |
| Study Group use of country names as TLD | Survey UNESCO Member States | August 2012 | Nov. 2012 | UNESCO | Survey Concluded |
|  | Survey ICANN community | Nov. 2012 No further steps taken |  | Paul Szyndler, Study Group | Not conducted |
|  | Draft Advise WG | December 2012 | meeting | Chair of WG | Publish before Durban meeting and public consultations Draft report was discussed at WG meeting in Beijing. Draft report was published and closed 30 August. |
|  | Final advise | 18 April 2013 | Buenos Aires 2013 | Chair WG | Chair will submit before the BA to enable |

| ccTLD community related activities version May 2013 |
| --- |
| Activity | Description | Launch date | End Date | Owner | Description |
| Financial contr. | Model for ccTLD contribution to ICANN |  |  | Byron Holland | Model Finalized |
|  | Distribution of contribution model |  |  | Byron Holland | To be further discussed by WG before BA meeting. Continuing |
| Tech WG | Tech Day programme Durbanmeeting Eberhard Lisse Tech Day. |
| Strategic and Ops plan | Submissions SOP WG on ICANN Strat and Ops Plan and Budgetplan | 1 November 2012 | 20 December 2012 | Roelof Meijer | Awaiting next initiatives Strat and Ops Plan. Anticipated to start again prior to BA meeting (Strat Planning process) |
| ccNSO Statement Geographic Regions Fnal Report | The ccNSO Council resolved to submit a ccNSO Statement on the GEographc Regions WG Final Report | 17 July 2013 | 16 Ocotber | Paul Szyndler(porposed) | Appointment of drafting team to be completed by 6 September |
| Incident response repository WG |  |  | Buneos Aires Meeting | Luis Diego Espinoza | WG prepares report, |
| Overview Administrative Activities May 2013 2012 |
| Activity | Description | Launch | Target Date | Chair/ owner | Pending action/status/dependency |
| Council Elections | Council election FY 2014 | 10 September 2013 |  | Election manager | Appointment of Election manager, approval of timeline |
| Board member Election | Term Board seat 11, expires at Annual meeting FY 2014. To allow selected Board member to participate in time, election prepared. | 10 September 2013 | 31 January 2014 | Election Manager | Appointment of Selection manager, approval of timeline |
| Meetings Programme |  |  |  |  |  |
|  | Prepare ccNSO Buenos Aires Meeting | September 2014 | November 2014 | Chair Program | First meeting, including analysis survey results. Draft agenda is prepared and will be posted. Panel discussion topic: TBD |
| Chair Election | Chair steps down at the Durban meeting |  | 17 July 2013 | ccNSO Council | Election of chair of Council |
| Assign Council roles and responsibilities | 20 March 2013 |  | 10 April 2013 | Chair of the ccNSO | Completed and published |
| Council Triage committee |  |  | 1 July 2013 | ? To be appointed (vice-chair) | Triage committee has submitted set of recommendations. Hong Xue appointed as new member, replacing Mary Wong Seek and appoint new member to replace Byron Holland |
| Rules and Guidelines update | Update ccNSO Council Election Guidelines, and improvement voting system | 20 November 2012 | TBD | Katrina Satarki | Based on incidents during 2012 Council elections, procedures need to be updated. Appoint Council Committee, propose to the community at the Beijing meeting. Council committee appointed December 11, 2012. Chair appointed (Katrina Satarki) Further refine election Guidelines, assist in improvement/renewal of voting tool. |
| Study Group Quorum rule review |  |  |  | Katrina Sataki | Establish study group to assess need for quorum rule in voting (ccNSO Bylaws, ccNSO Rules) Charter has been adopted. Call for Volunteers were appointed by email decision of the Council per 6 September 2013. |
| ccNSO Workplan review | Update overview of activities and adjust portfolio for 2013-2015 timeframe | 1 March 2013 | 10 April 2013 | Chair of the ccNSO/ Senior policy advisor | Discussed at workshop. |
| Update ccNSO Rules and Guidelines to include IDN ccTLD in ccNSO | The current set of Rules and Guideliens needs to be updated to reflect the updates to Article IX and Annex B of the ICANN Bylaws as a result of inclusion of IDN ccTLD in the ccNSO |  | Post Buenos Aires meeting (in conjunction with adoption of the changes to Article IX and Annex B of the ICANN Bylawas resulting from the IDN ccTLD ccPDP. | Chair/senior policy advisor | Update Guideline for establishing WG and Workplan to include recommendations of ccNSO Council capacity and workload study group |
| ccNSO Translation Policy | Planning Implementation of tools on website |  |  | Staff | Completed. This completes ccNSO Imporvemnets |
| 10th Anniversary ccNSO | Council and ccNSO appointed Board members committee, to organise festivties 10th Anniversary ccNSO in June 2013 | 20 November | Completed | Vika Mpisane |  |