## Slide 1
GNSO Review Update
Jen Wolfe | GNSO Council Meeting | 19 March 2015

## Slide 2: GNSO Review Timeline (revised 9 March)
20 March
24 April
1 June
20 July
30 August
Extended
Comments on Working Text due to Westlake
Draft Report for GNSO Review WP Consideration
Public Comment on Draft Report Opens
Public Comment Closes
Final Report Issued by Westlake
Timeline has been revised to include multiple additional opportunities for the GNSO Review Working Party to continue the ongoing process of providing feedback to Westlake
The schedule has been extended by 6 weeks in the last revision. Overall, the GNSO Review process has been extended from 9 months to 14 months.
Highlights:
GNSO Review Working Party session with Westlake (if needed)
Continued feedback

## Slide 3: Next Steps
Working Text Comments Due
The GNSO Review Working Party to deliver comments on working text to Westlake
March 20
April 24
May 4 and 12
May 15
Draft Report v.0
Westlake delivers Draft Report v.0 to GNSO Review Working Party, along with a summary of disposition of comments and feedback from GNSO Review Working Party
Working Party Sessions
Working sessions have been scheduled for 4 May and, if necessary, 12 May
Draft Report v.0 Comments Due
The GNSO Review Working Party to deliver comments on Westlake’s Draft Report v.0
June 1 – July 20
Draft Report v.1 Posted for Public Comment
Draft Report v.1 from Westlake posted for Public Comment
Notes: Look for different ways to display your data or text but using alternatives to simple bullets.
To adjust the number in the arrow to text or another number, click on the text box around the number, revise.
To add an arrow, click on the arrow, ensure the arrow is highlighted, COPY and PASTE and move to the desired placement, or DELETE if there are too many arrows.

## Slide 4: Next Steps (cont’d)
ICANN53
GNSO Review Working Party update to GNSO Council/Community and working session with Westlake
June 21-26
July TBD
August 3-17
August 30
Working Party Sessions
Working Party sessions with Westlake to be scheduled during the weeks of 6 July and 27 July, if necessary
Public Comment
Community review of Report of Public Comments Received
Final Report
Final report published
Update the SIC
Information on the status of the GNSO Review Working Party will be provided to the SIC
April 24-26 & June 19
Notes: Look for different ways to display your data or text but using alternatives to simple bullets.
To adjust the number in the arrow to text or another number, click on the text box around the number, revise.
To add an arrow, click on the arrow, ensure the arrow is highlighted, COPY and PASTE and move to the desired placement, or DELETE if there are too many arrows.

## Slide 5: Review Statistics
178 completed online questionnaire
300 started
60% completion rate
40 one on one interviews
Westlake’s work in process
5 written comments from WP members
21 participants in working session on 3 March
15 GNSO Working Party Meetings
21 GNSO members
3 webinars
14 presentations
2 blogs + 2 videos
3,000 brochures & postcards
1,709 views of Announcements
2,957 blog views
446 visits to community wiki
(as of Jan 2015)
360 Assessment
Interviews
Working Text
WP Meetings
Outreach
Engagement

## Slide 6: Useful Links and Q&A
Thank You and Questions
GNSO Review Working Party Home Page
Independent Examiner Information
Working Text and 360 Assessment Responses
GNSO Review Working Party Activities, Milestones and Statistics
GNSO Review Working Party Comments to Westlake's Working Text
Notes: You can adjust the email/web address to whichever email or web address is best suited to your presentation. This should be your final slide.