New gTLD Workshop Plans

8 October 2007

The purpose of this document is to outline plans for a comprehensive workshop regarding the Introduction of New gTLDs:

- The workshop is currently scheduled for six hours on Monday afternoon, 29 October, 1 pm to 7 pm.

- Best efforts have been made to minimize scheduling conflicts with other meetings by all key stakeholders:  GNSO, ccNSO, GAC, ALAC, and the ICANN Board.

- The primary goals of the workshop are to provide:

  - A comprehensive but brief overview of the recommendations approved by the GNSO Council for the Introduction of New gTLDs as developed in the associated Dec05 PDP, including:

      - The principles and implementation guidelines approved with the recommendations

      - Key issues considered

      - Rationale for final decisions

      - Implementation considerations

      - Work on implementation plans to date.

  - A thorough opportunity for an interactive session involving online and audience participants, GNSO Councilors, New gTLD Committee members and ICANN Staff.

The following people participated in developing this plan with review and comments requested of the full GNSO Council:

- Adrian Kinderis

- Avri Doria

- Chuck Gomes

- Craig Schwartz

- Denise Michel

- Karen Lentz

- Karla Valente (newly hired New gTLD Program Director).

- Kristina Rosette

- Kurt Pritz

General Guidelines

- Provide a structured session that facilitates discussion in an organized fashion

- The moderator should clearly communicate expectations regarding how the workshop will be run including:

  - Brief overview of the agenda

  - Participation rules

- Try to achieve a good balance between panel and audience participation, while realizing that some items may involve more presentation than interaction

- Avoid re-debate of the issues by panel and/or Council members

- Organize the workshop into separate sessions by dividing principles, recommendations and implementation guidelines into thematic groups, each of which will be the focus of a separate interactive session

- Each session should consist of the following:

  - Brief presentation (by one or more panel members)

  - Guided interaction with the audience including consideration of questions submitted in advance

  - Open interaction with the audience.

- Councilors, New gTLD Committee members and ICANN Staff members who are not on the panel should be encouraged to participate with other audience participants during the interactive session using a special microphone set up for that purpose, but in doing so, they should:

  - Set good examples for being concise and to the point

  - Try to add additional clarity regarding how the committee arrived at the final positions

  - Aim to reinforce the decisions made by the committee and the Council

  - Avoid using this forum to re-attempt to make changes that were not accepted in the PDP work or by the Council.

- All Council members should support the recommendations in a way that is constructive with the goal of increasing understanding of the thought processes that happened in the PDP process that led to the final recommendations.

- Reading of lengthy portions of the report should be avoided; instead

  - Those with online access during the meeting should be encouraged to link to the report; hard copies at least for Part A of the report should be available for those who do not have on-line access.

  - Clear reference to well-identified sections of the report should be made when the need arises.

  - Participants should be encouraged to read relevant portions of the report on their own.

Session Breakdown

Here is a brief outline of each of the three workshop sessions.  A more detailed description is provided in Attachment A that includes a complete listing of the applicable principles, recommendations and implementation guidelines.

Session 1

- Moderator presentation

  - Background

  - Workshop Instructions - include URLs and availability of printed copies of reference documents

  - Summary of Council vote re. the recommendations

- Panel presentation(s)

  - Principles A-F

  - Recommendations 1, 4, 9, 10, 16, 17, 19

  - Implementation Guidelines IG A – IG E, IG J – IG L

  - Overview of Draft RFP

  - Overview of Draft Base Contract

  - Projected Timeline

  - Estimated Costs

  - Other Implementation Details

- Responses to questions submitted in advance (if not already answered)

- Live Q&A

Session 2

- Panel presentation(s)

- Recommendations 2, 5, 7, 8, 13, 14, 15, 18

- Implementation Guidelines IG I – IG O

- Other Implementation Details

- Responses to questions submitted in advance (if not already answered)

- Live Q&A

Session 3

- Panel presentation(s)

  - Principle G

  - Recommendations 3, 6, 12, 20

  - Implementation Guidelines IG F, IG G, IG H, IG P, IG Q, IG R

  - Other Implementation Details

- Responses to questions submitted in advance (if not already answered)

- Live Q&A

Panel Members

The following assumptions were made in developing a list of panel members:

- Having people on panels who are topically prepared is more important than having every constituency represented.

- Panel size should be kept to a minimum to maximize time efficiency.

The primary criterion for panel member recommendations was significant participation in the New gTLD Committee, not just working groups of that committee.

Chris Disspain, chair of the ccNSO, will be the Workshop moderator.

- A conference call with Chris will be held on 10 October (11 October in Melbourne) to provide him information and answer his questions.

- An in-person meeting with Chris and panel members will be held in L.A. the weekend before the workshop.

The following  have agreed to participate as panel participants.

- Session 1:  Tony Harris (ISCPC), Ute Decker (IPC), Mike Rodenbaugh (CBUC), Jon Nevett (RC), Avri Doria (Council Chair), Chuck Gomes (Council Vice Chair), Kurt Pritz (Staff representative)

- Session 2:  Ray Fassett (RyC), Mawaki Chango (NCUC), Tony Harris (ISCPC), Avri Doria (Council Chair), Chuck Gomes (Council Vice Chair), Kurt Pritz (Staff representative)

- Session 3:  Robin Gross (NCUC), Kristina Rosette (IPC), Jon Bing (NomCom), Marilyn Cade (BC), Avri Doria (Council Chair), Chuck Gomes (Council Vice Chair), Kurt Pritz (Staff representative)

Logistical Arrangements

- The workshop should be announced as early as possible prior to the workshop date with strong encouragement for potential participants to review the full report in advance with particular focus on the principles, recommendations and implementation guidelines.

- Reminders of the workshop should be sent out periodically leading up to the meeting, again encouraging potential participants to review the full report in advance with particular focus on the principles, recommendations and implementation guidelines.

- As soon possible before the workshop an outline of the structure of the workshop should be communicated including explanation of the content of each separate session.

- All communications above should occur in multiple forms: web posting; direct email to key ICANN groups: GNSO, ccNSO, GAC, ALAC, and the ICANN Board; other distribution channels.

- A summary of the GNSO Final Report on the Introduction of New gTLDs and related activity will be posted and distributed as soon as possible before the workshop.

- Community members should be invited to submit questions in advance of the workshop if they so desire.

  - Staff will take the lead in soliciting questions.

    - Solicitation will happen:

      - With meeting announcements

      - When the agenda is distributed

      - When the summary document is distributed

      - Using other means as applicable.

    - To facilitate solicitation, collating and responding to questions, the following ideas were suggested:

      - Using a standard form (template)

      - Asking questioners and commenters to identify the principle(s), recommendation(s) and implementation guideline(s) for which they are commenting or asking questions

      - If possible, allowing questions to be submitted in a few languages other than English, translating them into English for response purposes and translating the responses back into the language used by the questioner.

  - Staff will collate questions received and will publicly archive them.

  - Plans for responding to advance questions are still being worked; ideas under consideration include:

    - Forming a small group and assigning questions to group members

    - Using advance questions to shape presentations and live Q&A

    - Treating opinion comments differently from questions

    - Using the public archive to respond to questions.

- Regarding advance questions from the community:

  - As possible, questions should be answered even if they are not answered in the workshop.

  - Questions should be distributed to panelists and the moderator in advance.

  - As feasible, the public participation site should be used to answer questions.

  - The moderator and/or panelists should try to ensure that advance questions are answered during the appropriate panel if the questions have not already been answered.

- A cheat sheet of principles, recommendations and implementation guidelines will be prepared and posted prior to the workshop with printed copies available at the workshop including links to applicable PDFs. – (Staff members are taking a crack at this.)

- Panel members, Councilors and Staff members should be available on breaks as much as possible, noting that panel members especially may need a brief break before being available.  The moderator should ask Councilors and Staff members not on the current panel to stand up just before breaks so that they can be easily identified.

- Name tags will be provided and worn by panel members, Councilors and Staff members to make it easy for audience members to identify them during breaks and thereby facilitate ongoing dialog.

- Seating should be reserved near the front with a nearby microphone designated for restricted use by Councilors and ICANN staff members not on the current panel.

- To allow time for full Council review and input in advance, as soon as possible prior to the L.A. meetings, PowerPoint presentations should be prepared for each panel:

  - Presentations should be as brief as possible with time allocated to topics based on their level of possible controversy and complexity.

    - Topics predicted to generate minimal controversy should be covered very briefly, possibly by simply repeating the report wording.

    - Topics predicted to generate more controversy should be covered in more detail including but not limited to describing:

      - The different issues that the committee considered in reaching the final recommendation

      - Alternative approaches considered

      - Reference to relevant public comments received that introduced new considerations (i.e., those not already discussed by the committee and/or Council)

      - Minority opinions

      - The key points underlying the rationale for the recommendation.

  - Session 1 will include workshop instructions and background information.

  - Regarding how much time should be spent in presentations on the introduction of new gTLDs not directly related to the principles, recommendations and implementation guidelines  (e.g., RFP, base contract, implementation details):

    - Implementation details should be provided as available.

    - Estimated timeline and costs should be discussed. (It is unlikely that detail will be available on these, especially costs.)

    - High level outline of the RFP and base contract should be given but discussion should be deferred to public comment period that will be provided specifically for those items.

- During the workshop the moderator should be provided access to live ICANN Wiki questions submitted and should weave them into Q&A time.

- There will be some simultaneous translation in the workshop.

  - Will it be possible for questions to be asked in a language for which simultaneous translation is offered and then translate the questions into English for the panel and audience?

- Name cards should be prepared and displayed for the moderator and all panel participants.

- All presentations should be preloaded in one central location for easy of display and timeliness of display.

Attachment A:  Session Breakdown

Session 1

- Moderator presentation

  - Background

  - Workshop Instructions - include URLs and availability of printed copies of reference documents

  - Summary of Council vote re. the recommendations

- Panel presentation(s)

- Principles A-F

- Recommendations 1, 4, 9, 10, 16, 17, 19

- Implementation Guidelines IG A – IG E, IG J – IG L

- Overview of Draft RFP

- Overview of Draft Base Contract

- Projected Timeline

- Estimated Costs

- Other Implementation Details

- Responses to questions submitted in advance (if not already answered)

- Live Q&A

Principles

A.	New generic top-level domains (gTLDs) must be introduced in an orderly, timely and predictable way.

B.	Some new generic top-level domains should be internationalised domain names (IDNs) subject to the approval of IDNs being available in the root.

C.	The reasons for introducing new top-level domains include that there is demand from potential applicants for new top-level domains in both ASCII and IDN formats. In addition the introduction of new top-level domain application process has the potential to promote competition in the provision of registry services, to add to consumer choice, market differentiation and geographical and service-provider diversity.

D.	A set of technical criteria must be used for assessing a new gTLD registry applicant to minimise the risk of harming the operational stability, security and global interoperability of the Internet.

E.	A set of capability criteria for a new gTLD registry applicant must be used to provide an assurance that an applicant has the capability to meets its obligations under the terms of ICANN’s registry agreement.

F.	A set of operational criteria must be set out in contractual conditions in the registry agreement to ensure compliance with ICANN policies.

Recommendations

      - ICANN must implement a process that allows the introduction of new top-level domains.

The evaluation and selection procedure for new gTLD registries should respect the principles of fairness, transparency and non-discrimination.

All applicants for a new gTLD registry should therefore be evaluated against transparent and predictable criteria, fully available to the applicants prior to the initiation of the process. Normally, therefore, no subsequent additional selection criteria should be used in the selection process.

4.	Strings must not cause any technical instability.

9.	There must be a clear and pre-published application process using objective and measurable criteria.

10.	There must be a base contract provided to applicants at the beginning of the application process.

16.	Registries must apply existing Consensus Policies and adopt new Consensus Policies as they are approved.

17.	A clear compliance and sanctions process must be set out in the base contract which could lead to contract termination.

19.	Registries must use only ICANN accredited registrars in registering domain names and may not discriminate among such accredited registrars.

Implementation Guidelines

IG A	The application process will provide a pre-defined roadmap for applicants that encourages the submission of applications for new top-level domains.

IG B	Application fees will be designed to ensure that adequate resources exist to cover the total cost to administer the new gTLD process.  Application fees may differ for applicants.

IG C	ICANN will provide frequent communications with applicants and the public including comment forums.

IG D	 A first come first served processing schedule within the application round will be implemented and will continue for an ongoing process, if necessary.  Applications will be time and date stamped on receipt.

IG E	The application submission date will be at least four months after the issue of the Request for Proposal and ICANN will promote the opening of the application round.

Session 2

- Panel presentation(s)

- Recommendations 2, 5, 7, 8, 13, 14, 15, 18

- Implementation Guidelines IG I – IG O

- Other Implementation Details

- Responses to questions submitted in advance (if not already answered)

- Live Q&A

Recommendations

2.	Strings must not be confusingly similar to an existing top-level domain or a Reserved Name.

5.	Strings must not be a Reserved Word.

7.	Applicants must be able to demonstrate their technical capability to run a registry operation for the purpose that the applicant sets out.

8.	Applicants must be able to demonstrate their financial and organisational operational capability.

13.	Applications must initially be assessed in rounds until the scale of demand is clear.

14.	The initial registry agreement term must be of a commercially reasonable length.

- There must be renewal expectancy.

18.	If an applicant offers an IDN service, then ICANN’s IDN guidelines must be followed.

Implementation Guidelines

IG I	An applicant granted a TLD string must use it within a fixed timeframe which will be specified in the application process.

IG J	The base contract should balance market certainty and flexibility for ICANN to accommodate a rapidly changing market place.

IG K	ICANN should take a consistent approach to the establishment of registry fees.

IG L	The use of personal data must be limited to the purpose for which it is collected.

IG M	ICANN may establish a capacity building and support mechanism aiming at facilitating effective communication on important and technical Internet governance functions in a way that no longer requires all participants in the conversation to be able to read and write English.

IG N	ICANN may put in place a fee reduction scheme for gTLD applicants from economies classified by the UN as least developed.

IG O	ICANN may put in place systems that could provide information about the gTLD process in major languages other than English, for example, in the six working languages of the United Nations.

Session 3

- Panel presentation(s)

  - Principle G

  - Recommendations 3, 6, 12, 20

  - Implementation Guidelines IG F, IG G, IG H, IG P, IG Q, IG R

  - Other Implementation Details

- Responses to questions submitted in advance (if not already answered)

- Live Q&A

Principles

G.	The string evaluation process must not infringe the applicant’s freedom of expression rights that are protected under internationally recognized principles of law.

Recommendations

3.	Strings must not infringe the existing legal rights of others that are recognized or enforceable under generally accepted and internationally recognized principles of law.

Examples of these legal rights that are internationally recognized include, but are not limited to, rights defined in the Paris Convention for the Protection of Industry Property (in particular trademark rights), the Universal Declaration of Human Rights (UDHR) and the International

Covenant on Civil and Political Rights (ICCPR) (in particular freedom of expression rights).

6.	Strings must not be contrary to generally accepted legal norms relating to morality and public order that are recognized under international principles of law.

Examples of such principles of law include, but are not limited to, the Universal Declaration of Human Rights (UDHR), the International Covenant on Civil and Political Rights (ICCPR), the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) and the International Convention on the Elimination of All Forms of Racial Discrimination, intellectual property treaties administered by the World Intellectual Property Organisation (WIPO) and the WTO Agreement on Trade-Related Aspects of Intellectual Property (TRIPS).

20.	An application will be rejected if an expert panel determines that there is substantial opposition to it from a significant portion of the community to which the string may be explicitly or implicitly targeted.

- Dispute resolution and challenge processes must be established prior to the start of the process.

Implementation Guidelines

IG F	If there is contention for strings, applicants may:

i)	resolve contention between them within a pre-established timeframe

ii)	if there is no mutual agreement, a claim to support a community by one party will be a reason to award priority to that application.  If there is no such claim, and no mutual agreement a process will be put in place to enable efficient resolution of contention and;

iii)	the ICANN Board may be used to make a final decision, using advice from staff and expert panels.

IG G	Where an applicant lays any claim that the TLD is intended to support a particular community such as a sponsored TLD, or any other TLD intended for a specified community, that claim will be taken on trust with the following exceptions:

(i)	the claim relates to a string that is also subject to another application and the claim to support a community is being used to gain priority for the application; and

(ii)	a formal objection process is initiated.  Under these exceptions, Staff Evaluators will devise criteria and procedures to investigate the claim.

Under exception (ii), an expert panel will apply the process, guidelines, and definitions set forth in IG P.

IG H	External dispute providers will give decisions on objections.

IG P	The following process, definitions, and guidelines refer to Recommendation 20.

Process

Opposition must be objection based.

Determination will be made by a dispute resolution panel constituted for the purpose.

The objector must provide verifiable evidence that it is an established institution of the community (perhaps like the RSTEP pool of panelists from which a small panel would be constituted for each objection).

Guidelines

The task of the panel is the determination of substantial opposition.

  - substantial

In determining substantial the panel will assess the following: significant portion, community, explicitly targeting, implicitly targeting, established institution, formal existence, detriment.

  - significant portion

In determining significant portion the panel will assess the balance between the levels of objection submitted by one or more established institutions and the level of support provided in the application from one or more established institutions.

The panel will assess significance proportionate to the explicit or implicit targeting.

  - community

Community should be interpreted broadly and will include, for example, an economic sector, a cultural community, or a linguistic community.  It may also be a closely related community which believes it is impacted.

  - explicitly targeting

Explicitly targeting means there is a description of the intended use of the TLD in the application.

  - implicitly targeting

Implicitly targeting means that the objector makes an assumption of targeting or that the objector believes there may be confusion by users over its intended use.

  - established institution

An institution that has been in formal existence for at least 5 years. In exceptional cases, standing may be granted to an institution that has been in existence for fewer then 5 years.  Exceptional circumstances include but are not limited to re-organisation, merger, or an inherently younger community.

The following ICANN organizations are defined as established institutions: GAC, ALAC, GNSO, ccNSO, ASO.

  - formal existence

Formal existence may be demonstrated by:  appropriate public registration, public historical evidence, validation by a government, intergovernmental organization, international treaty organisation or similar.

  - detriment

The objector must provide sufficient evidence to allow the panel to determine that there would be a likelihood of detriment to the rights or legitimate interests of the community or to users more widely.

IG Q	ICANN staff will provide an automatic reply to all those who submit public comments that will explain the objection procedure.

IG R	Once formal objections or disputes are accepted for review there will be a cooling off period to allow parties to resolve the dispute or objection before review by the panel is initiated.