TABLE OF CONTENTS (click on the link below to go directly to the project in this list).

.

| Category | Title | Abbreviation |
| --- | --- | --- |
| GNSO WG/DT | GNSO Improvements Standing Committee on Improvement Implementation | SCI |
| GNSO WG/DT | Drafting Team on Cross-Community Working Groups | CWG-DT |
| GNSO WG/DT | IRTP Part D PDP Working Group | IRTP Part D |
| GNSO WG/DT | Policy & Implementation Working Group | PI |
| GNSO WG/DT | GNSO Data & Metrics for Policy Making WG | DMPM |
| GNSO WG/DT | RAA Privacy & Proxy Services Accreditation Issues | P&P |
| GNSO WG/DT | Translation/Transliteration of Internationalized Registration Data | T&T |
| Other | WHOIS Studies | WHO1 |
| Other | Purpose of Whois Issue Report (DEFERRED PENDING EWG FINAL REPORT) | Whois PDP |
| Other | Protection of Intergovernmental Organization Names in All gTLDs | IGO-INGO |
| Other | Issue Report on curative protections of the UDRP/URS for IGO/INGOs |  |
| Other | Uniform Dispute Resolution Policy (COMPLETED FOR NOW) | UDRP |
| Joint WG/DT | Geo Regions Review Community-wide Working Group | GEO |
| Joint WG/DT | Joint ccNSO-GNSO Internationalized Domain Names Working Group (JIG) | JIG |
| Implementation | IRTP Part B Adopted Recommendations | IRTP Part B |
| Implementation | Inter-Registrar Transfer Policy Part C PDP | IRTP Part C |
| Implementation | Locking of a domain name subject to UDRP proceedings PDP | Lock |
| Implementation | ‘Thick’ WHOIS PDP | Thick WHOIS |

Last updated: 18 February 2014

This list includes GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| GNSO Working Groups / Work Teams / Drafting Teams |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| GNSO Standing Committee on Improvements Implementation (SCI) Chair: Ron Andruff Vice-Chair: Cintra Sooknanan Council liaison : Avri Doria Staff: J. Hedlund, M. Wong, M. Konings The GNSO Standing Committee on Improvements Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. It was recently confirmed as a standing committee by the GNSO Council. | 2011-Apr-07 | Ongoing | SCI | The SCI is working on the following topics: - Voting by email; - Waiver under the GNSO Operating Procedures; - Consensus scale definitions in the current WG Guidelines. The SCI’s proposed recommendations for the WG self-assessment survey as well as re-submitting a motion were published for public comment on 10 February. Comments may be submitted until 3 March, followed by a reply period, if applicable. |
| Cross-Community Working Groups Framework Drafting Team GNSO Council Co-Chair: John Berard ccNSO Council Co-Chair: Becky Burr Staff: M. Wong,, Bart. Boswinkel ccNSO Council Co-Chair: Becky Burr The CWG Framework Drafting Team was formed to develop a charter for a Working Group that will further refine the principles for the formation, operation and termination of cross-community working groups. | 19 May 2011 | Ongoing | DT | The first meeting of the DT is being organized for end-February 2014, to discuss a draft charter for the WG. |
| IRTP Part D PDP WG Co-Chair: James Bladel, Mikey O’Connor Council Liaison: Volker Greimann Staff: L. Hoffmann, M. Konings. PDP on the remaining IRTP issues which include: - Reporting requirements for registries and dispute providers in relation to the TDRP; - How to handle disputes when multiple transfers have occurred in the TDRP; - Should dispute options for registrants be developed; - Should there be requirements or best practices for registrars to make information on transfer dispute resolution options available; - Are existing penalties for policy violations sufficient; - Have EPP AuthInfo codes eliminated the need for FOAs. | 17 Oct 2012 | Ongoing | WG | The WG continues to meet on a weekly basis. The WG is finalising its Initial Report and is targeting to publish it for public comment in time for the 3 March Singapore Meeting submission deadline. The Group will present its recommendations during a F2F Community Workshop at the ICANN meeting in Singapore. |
| Policy & Implementation WG Co-Chairs: Chuck Gomes, J. Scott Evans Council Liaison: Amr Elsadr and Brian Winterfeldt Staff: M. Konings, M. Wong The WG is tasked to provide the GNSO Council with a set of recommendations on: - A set of principles that would underpin any GNSO policy and implementation related discussions - A process for developing gTLD policy, perhaps in the form of “Policy Guidance”, including criteria for when it would be appropriate to use such a process (for developing policy other than “Consensus Policy”) instead of a GNSO Policy Development Process; - A framework for implementation related discussions associated with GNSO Policy Recommendations; - Criteria to be used to determine when an action should be addressed by a policy process and when it should be considered implementation, and; - Further guidance on how GNSO Implementation Review Teams are expected to function and operate. | 9 May 2013 | Ongoing | WG | The sub-team on Working Definitions has submitted a final draft to the full WG for discussion. The Working Principles sub-team expects to finalize its draft within the next few weeks. The WG has solicited community feedback on a set of initial questions, and will shortly be reviewing any feedback received. |
| GNSO Data & Metrics for Policy Making WG (DMPM) Chair: TBD Council Liaison: M. O’Connor Staff: B. Cobb, L. Hoffmann The WG is tasked to provide the GNSO Council with a set of recommendations on: - A set of principles that may compliment any GNSO policy efforts related to metric/data requirements to better inform the policy development process; - A process for requesting metrics and reports both internal to ICANN or external, including GNSO contracted parties; - A framework for distributing metrics and reports to Working Groups, the GNSO Council and the GNSO as a whole; - Changes, if any, to existing Working Group Guidelines and work product templates | 17 Oct 2012 | On-going | Staff | The GNSO Council has adopted the WG’s Charter and a call for volunteers has been published. The Group is expected to start its work in the coming weeks. The Group also plans to meet face-to-face during the ICANN meeting in Singapore. |
| Privacy & Proxy Services Accreditation Issues PDP WG Chair: Don Blumenthal Council Liaison: Maria Farrell Staff: M. Wong, M. Konings The Registrar Accreditation Agreement (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which have been identified as those relating to privacy & proxy services and their accreditation, will be examined in this PDP. | 2009 May-21 | Ongoing | WG | The WG has solicited feedback on the questions in the WG Charter from GNSO SGs and Constituencies, and from other SOs and ACs. It has developed an initial Work Plan and will begin deliberations on the WG Charter questions in mid-February. |
| Translation/Transliteration of Internationalized Registration Data PDP WG Chair(s): Chris Dillon, Rudi Vansnick Council Liaison: Ching Chiao Staff: J. Hedlund/L. Hoffmann The Council approved the initiation of a PDP on translation and transliteration of contact information on 13 June 2013. | 17 Oct 2012 | Ongoing | WG | The WG was formed and has begun weekly meetings. The WG has selected Chris Dillon and Rudi Vansnick as Co-Chairs. The WG approved a Work Plan and has sent requests for input on the PDP issues to the SOs and ACs. It is discussing key questions concerning the issues identified in its charter and the responses received to its requests for input. |

| Other GNSO Activities |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| STUDIES |  |  |  |  |
| WHOIS Studies Staff: Mary Wong The GNSO Council approved several studies of WHOIS. Topics include Misuse of WHOIS Data, Registrant Identification Information, Proxy and Privacy “Abuse” and Proxy and Privacy “Relay” and “Reveal”. Budget was approved by the ICANN Board for these studies. | 2007 Oct-31 | Ongoing | Staff | Staff is overseeing four studies of WHOIS as requested by the GNSO, the last of which are now nearing completion: - A Misuse of Public gTLD WHOIS Data Study – conducted by researchers at Carnegie Mellon University (CMU). The study was released for public comment on 27 November 2013 and closed on 18 January 2014. Staff analysis of public comments received has been published, and CMU is finalizing its Final Report for publication. - A Registrant Identification Study –launched in October 2011, with draft analysis by NORC. The Final Report has been published. - A Proxy/ Privacy “Abuse” Study – conducted by the National Physical Lab of the UK (NPL). The study was released for public comment on 24 September 2013. Staff analysis of public comments received has been published. A final report incorporating responses to the public comments received is in process. - A pre-study “survey” on Proxy/Privacy “Relay” and “Reveal” – final report [PDF, 1.23MB] has been published and this study is now completed. |

| AWAITING COUNCIL ACTION |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |

| Staff Implementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Issue Report on the purpose of collecting and maintaining gTLD registration data and on solutions to improve accuracy and access to gTLD registration data. Staff: M. Wong, M. Konings, L. Hoffmann | 2012-Nov-8 |  | Staff | The Board resolution on the Whois RT Recommendations (see http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm) directs preparation of an Issue Report on the purpose of collecting and maintaining gTLD registration data, and on solutions to improve accuracy and access to gTLD registration data, as part of a Board-initiated GNSO policy development process. The Preliminary Issue Report was published for public comment on 15 March 2013. The comment forum closed on 13 May. A Final Issue Report will be published following the finalization of the EWG recommendations. |
| Protection of Intergovernmental Organization Names in New gTLDs Staff: B. Cobb, M. Wong Chair: Thomas Rickert Council Liaison: | April 2012 | Apr 2014 | Board | The GNSO Council unanimously approved the motion on the IGO-INGO WG’s recommendations at its 20 Nov 2013 meeting. The NGPC of the ICANN Board is now considering the GNSO Recommendations in conjunction with the GAC advice, with a view toward developing a proposal for full Board consideration (http://www.icann.org/en/groups/board/documents/resolutions-07feb14-en.htm) |
| Issue Report on curative protections of the UDRP/URS for IGO/INGOs Staff: M. Wong, B. Cobb | 20 Nov 2013 | Mar 2014 | Staff | On the recommendation of the IGO-INGO PDP Working Group, the GNSO Council requested an Issue Report on exploring whether the curative rights of the UDRP and URS can be used by organizations that are granted based on their identified designations. An extension to deliver the Issue Report to the Council was granted and the Preliminary Issue Report is expected to be published for public comment at the end of February 2014. |

| INACTIVE PROJECTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Uniform Dispute Resolution Policy Issue Report Staff: Request for an Issue Report on the current state of the UDRP. | 2011-Feb-03 | Completed for now (with further Issue Report due in March 2015) |  | The GNSO Council deferred commencement of a PDP, except with regard to the lock issue. An Issue Report reviewing all rights protection mechanisms (current and developed for the New gTLD Program) including the UDRP and URS was requested by the GNSO Council, to be delivered eighteen months after the first delegation of new gTLDS (which occurred in October 2013). |

| Joint SO/AC Working Groups |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Joint ccNSO-GNSO IDN Working Group (JIG) ccNSO Co-chair: Yound Eum Lee GNSO Co-chair: E. Chung Staff: B. Boswinkel, S. Sheng, M. Wong This group identified three IDN issues of common interest and is proposing ways to resolve them: 1) Single character IDN ccTLDs and gTLDs; 2) aspects of variant management in the root zone; and 3) universal acceptance of IDN TLDs. Both the ccNSO and GNSO have extended this charter to continue into 2012. | 2009 July-23 | March 2014 | Board/Staff | Following the completion of the JIG’s work on the three key areas of work, but - has been, recognizing that further work needs to be done in relation to IDNs, in particular IDN variants and universal acceptance of IDNs, the GNSO and ccNSO Council requested the JIG to put forward suggestions on how to deal with these issues and deliver these suggestions to the GNSO Council by the ICANN Singapore Meetings in March 2014. |
| Geo Regions Review Community-wide Working Group Chair: Dave Archbold (ccNSO) GNSO Council Reps: Zahid Jamil and Ching Chiao Staff: R. Hoggarth This Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions. Changes could have broad impact, so this WG has representatives from most SOs and ACs. | 7 Aug 2008 | March 2014 | WG | The Working Group published its Final Report recommendations (see - http://www.icann.org/en/news/announcements/announcement-22jun13-en.htm) and circulated the Final Report to ICANN SOs and ACs (including the Council) for review and comment. The Council provided feedback to the WG Chair on 13 December 2013 (see http://gnso.icann.org/en/correspondence/robinson-to-archbold-13dec13-en.pdf). After all written SO-AC responses are submitted and reviewed by the WG, the Final Report of the WG will be shared with the Board for review. |

| Approved GNSO PDP Recommendations - Status (For Information Only) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Adopted | Target Date | Who holds Token | Pending action/status |
| IRTP Part B PDP Adopted Recommendations |  |  |  |  |
| 5. Promotion by ALAC and other ICANN structures of the measures outlined in a recent SSAC report: A Registrant's Guide to Protecting Domain Name Registration Accounts (SAC 044). (See http://gnso.icann.org/resolutions/#201106 for text of resolution) | 22 June 2011 |  | SOs/ACs | Chair of the GNSO Council has sent messages to the Chairs of ALAC, SSAC, ccNSO, GAC, ASO (see http://gnso.icann.org/mailing-lists/archives/council/msg11736.html) to inform them about the recommendation and open discussions. |
| IRTP Part B Recommendation #9 – part 2 The GNSO Council resolved in Singapore that prior to consideration of the recommendation which states: "denial reason #7 should be replaced by adding a new provision in a different section of the IRTP on when and how domains may be locked or unlocked", the GNSO Council requests ICANN Staff to provide a proposal for such a new provision, taking into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report - (Recommendation #9 - part 2). Upon review of the proposal, the Council will consider the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation and staff proposal at its meeting in Costa Rica. ICANN Staff has started working on the implementation of the recommendation and expects to announce the implementation plan shortly. |
| IRTP Part B Recommendation #8 The GNSO Council resolved in Singapore that prior to considering a recommendation to standardize and clarify WHOIS status messages regarding Registrar Lock status, the GNSO Council asked staff to provide a proposal to ensure that it is technically feasible to implement this recommendation. Staff should take into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report). (IRTP Part B Recommendation #8). The goal of these changes is to clarify why the Lock has been applied and how it can be changed. Upon review of the proposed plan, the Council will consider whether to approve the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation at its meeting on 6 May (see http://www.icann.org/en/groups/board/documents/resolutions-06may12-en.htm#1.5). ICANN Staff published the proposed implementation plan for public comment on 10 May 2013 (see http://www.icann.org/en/news/public-comment/wisp-10may13-en.htm). The Reply period for public comment closed on 24 June 2013. Staff expects to announce the implementation plan shortly. |
| IRTP Part C Recommendations |  |  |  |  |
| The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see http://gnso.icann.org/en/resolutions#20121017-4). | 17 Oct 2012 |  | Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December (see https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a). As instructed by the GNSO Council, an Implementation Review Team was formed. Meetings of the IRT have recently recommenced and further details on the proposed implementation are expected to be shared with the broader ICANN community by March 2014. |
| Locking of a Domain Name Subject to UDRP Proceedings Recommendations |  |  |  |  |
| The GNSO Council unanimously adopted the recommendations of the Locking of a Domain Name subect to UDRP Proceedings at its meeting of 1 August 2013. | 1 Aug 2013 |  | Staff | The ICANN Board adopted the Locking of a Domain Name subject to UDRP Proceedings at its meeting on 28 September (see http://www.icann.org/en/groups/board/documents/resolutions-28sep13-en.htm#1.c). As instructed by the GNSO Council, an Implementation Review Team was formed and met for the first time on 14 February to review the proposed timetable for the development of the implementation plan by ICANN staff. |
| Thick Whois PDP Recommendations |  |  |  |  |
| The GNSO Council adopted the recommendation to require Thick Whois for all gTLD registries at its meeting on 31 October 2013. | Nov 2012 |  | Staff | The ICANN Board approved the GNSO recommendations on Thick WHOIS at its meeting on 7 February 2014. (http://www.icann.org/en/groups/board/documents/resolutions-07feb14-en.htm). A call for volunteers will be circulated shortly to form the Implementation Review. Team. At the same time, staff will commence work on the development of an implementation plan. |

| Outstanding Recommendations for Council Action |  |  |
| --- | --- | --- |
| Description | Who holds Token | Pending action/status |
| None |  |  |