GNSO Council Restructuring Implementation Plan

Introduction and Outline

- Introduction and Summary (including explanation that restructuring implementation is separate (but parallel) track from PPSC and OSC efforts)

- Structure of Implementation/Transition Effort

- Key Process and Implementation Decisions/Issues

- Calendar of Timelines/Deadlines for Transition to/Implementation of Restructured GNSO Council

Key Process and Implementation Decisions to Effectuate Transition to Restructured GNSO Council (beyond first four bullets - not in any priority order):

- Determine form, structure and composition of implementation/transition oversight (drafting team, task force, working group, council subcommittee, etc.)

  - Decide whether  an oversight team is needed or whether the Council can handle this task directly – 20 Nov 08 (Rather than forming one oversight team, it might work for the Council to provide high level oversight and as needed form special drafting teams for specific subtasks.)

  - If it is decided to form an oversight team

    - Determine working method and decision-making mechanism of that TBD structure (consensus, majority, etc.); develop a charter

    - Develop a charter and initiate formation of the team – 18 Dec 08.

- Develop and confirm inventory of key process, transition and implementation decisions. – 8 Jan 09  (Note: this task could result in the addition and/or modification of implementation tasks.)

- Develop goals, milestones and timetable for decisions – 8 Jan 09 (Note: this task could result in the addition and/or modification of implementation tasks.)

- Establish form and frequency of update/reporting mechanism to Board.  8 Jan 09 (Once defined, recurring reports to the Board should probably be added to the tasks in this plan.)

- Chair Election for Restructured GNSO Council –

  - Determine appropriate timing (elect before, after or concurrent with new Council being seated); - 28 Feb 09 (Note: this task could result in the addition and/or modification of implementation tasks.)

  - As directed by Board, establish voting process beyond the first ballot. – Apr 09

- Identification and development of any additional voting thresholds or categories that may be needed (as directed by Board). – 4 Mar 09

- Apportionment mechanism for Nominating Committee Appointees – how are NCAs assigned to each house and the council-level position? – 4 Mar 09

- NCA criteria – supply guidance to Nominating Committee regarding qualification/factors to consider for future appointees? – 4 Mar 09

- Consider new and or continuing roles of liaison and observers from ALAC, GAC and ccNSO. – 4 Mar 09

- Consider application of geographic diversity considerations to selection of Council members. – 4 Mar 09 (It may be that this task needs to be completed earlier to allow enough time for Board action if needed and to also provide enough time for Stakeholder Groups to elect Councilors.)

- Consider implications for travel funding – 4 Mar 09

- Determine/define appropriate Council interface, if any, with stakeholder groups during transition (e.g., coordination, best practices or status reports). – 29 Jan 09

- Determine/define Council interface, if any, with constituency groups during transition (e.g., coordination, best practices or status reports). – 29 Jan 09

- Determine/define selection/seating/timing process for new council members in June 2009 and coordinate with constituencies/stakeholder groups as appropriate – need for clear understanding of whether new election/selections are necessary/appropriate? – 4 Mar 09

- Staggering of Council member terms to ensure smooth transitions in future? – 4 Mar 09

- Application of term limits - if approved by the Board. – 4 Mar 09

- Consider impact of June 2009 seating timetable on existing Council member terms and immediately subsequent Councilor terms? – 4 Mar 09

- Vice-Chair Selection process for each voting house – timing and mechanisms TBD by each voting house (potential post-June decision) – May 09

Please identify any others for discussion …..

Potential Calendar of Timelines/Deadlines for Transition to/Implementation of Restructured GNSO Council (does not include implementation of any other “improvements” matters being addressed by PPSC or OSC):

December 2008:

- GNSO Council restructuring implementation plan submitted in advance of the 11 December 2008 Board Meeting;

- Begin by-law mandated GNSO Council Chair Election process for existing Council (dates taken from GNSO Secretariat draft timetable):

Call for nominations for GNSO Council Chair
Monday 1 December 2008 to Monday 15 December 2008 (2 weeks)

Possible interviews with the candidates
Tuesday 16 December candidate slate announced

Proposed period to interview candidates
16 December - 23 December 2008

January 2009:

Voting for GNSO Council chair
Monday 5 January to 14 January 2009

Thursday 15 January 2009 announce the result of the GNSO Council Chair

Call for nominations for GNSO Council Vice Chair
Thursday 15 January 2009 to Thursday 22 January 2009

29 January 2009 GNSO Council meeting
Confirmation of the GNSO Council Chair
Vote for GNSO Council Vice Chair

30 January 2009 end of term for current Chair and Vice Chair

February 2009:

- Early February 2009 - Existing GNSO Constituencies submit confirmation documents to the Board for review in advance of the February 2009 Board Meeting;

March 2009:

- March 2009 – New GNSO Stakeholder Groups submit formal plans for Board approval for consideration at the 6 March ICANN Mexico City Board meeting;

- Board decision regarding GNSO constituency confirmations?

April 2009:

- April 2009 – Board decisions regarding Stakeholder Group plans?

- 30 April – Deadline for confirming decisions on all outstanding transition issues for restructured Council

May 2009:

- May 2009 – Board-approved Stakeholder Groups appoint/select/determine Council representatives

- New Council Chair election process confirmed

June 2009:

- June 2009 - Newly-structured GNSO Council is seated at the June 2009 GNSO Council meeting in Sydney, Australia.

# Comments

I don’t think the document will be big enough to justify a ToC but don’t feel strongly about this is others think it is useful.

I think this should be fairly straightforward, including a brief background and any applicable links along with an explanation as you note regarding the separate but parallel GNSO Improvements Implementation efforts.  An outline of the contents should be included here.

What is this? Is there some value in talking about the structure of the effort?  If not, this may not be needed.

Per my suggestion in my email response, I think these should be integrated.

I added possible subtasks and target dates.  I also think the document would be much more usable if the main tasks were numbered for easy reference instead of using bullets but I could not figure out how to change the format of the bullets in your document.

Suggest integration of the above into the following.