PDP – WT Timeline

| Target Date | What | Who | Status |
| --- | --- | --- | --- |
| 19 November | Distribution of draft report and recommendations for stage I and II | ICANN staff | Done |
| 25 November | Deadline for completing the survey on stage IV | All |  |
| 30 November | Open survey for stage IV | ICANN staff |  |
| 2 December | Review of draft report and recommendations for stage I and II | All |  |
| 3 December | Meeting of the PDP-WT – Review and discussion on draft report and recommendations for stage I and II & Discuss Stage IV Questions | All |  |
| 4 December | Distribution of draft report and recommendations for stage I, II and III | ICANN staff |  |
| 8 December | Distribute proposed issues and questions for stage V | ICANN staff |  |
| 9 December | Deadline for completing the survey for stage IV | All |  |
| 10 December | Tentative meeting of PDP-WT (Potential topic: Discuss Stage IV and/or V Questions) | All |  |
| 16 December | Review of draft report and recommendations for stage I, II and III & issues / questions for stage V | All |  |
| 17 December | Meeting of the PDP-WT – Review and discussion on draft report and recommendations for stage I, II and III & Discuss Stage V | All |  |
| 18 December | Open survey for stage V | ICANN staff |  |
| 18 December | Distribution of draft report and recommendations for stage I, II, III and IV |  |  |
| 4 January | Deadline for completing the survey for stage V | All |  |
| 6 January | Review of draft report and recommendations for stage I, II, III and IV | All |  |
| 7 January | Meeting of the PDP-WT – Review and discussion of draft report and recommendations for stage I, II, III and IV & Discussion on overarching issues | All |  |
| 11 January | Distribution of draft report for stage I, II, III, IV and V | ICANN staff |  |
| 18 / 19 January | Tentative Face-to-Face Meeting of the PDP-WT – Bring recommendations and discussions from all stages together to reach consensus on the new PDP, incl. overarching issues |  |  |
| 28 January | Distribution of draft Final Report on the new PDP (incorporating the report and recommendations for all stages as well as proposed by-law changes and overall design of PDP) | ICANN staff |  |
| 4 February | Meeting of the PDP-WT – Review and discussion of draft Final Report | All |  |
| 14 February | Deadline for comments to the draft Final Report | All |  |
| 15 February | Publication of Final Report for review and discussion at the ICANN Meeting in Nairobi | ICANN staff |  |
| 7-12 March | ICANN meeting in Nairobi – Presentation of Report to the ICANN Community and PPSC |  |  |
| 15 March | Opening of Public Comment Period |  |  |
| 15 April | Closing of Public Comment Period |  |  |
| 22 April | Meeting of the PDP-WT – Review and discussion of public comments received |  |  |
| 30 April | Revise Final Report, if appropriate, and submit to PPSC |  |  |