

| **Phase** | **Title** | **Links** |
| --- | --- | --- |
| **1 - Issue Identification** | **GNSO Council Action Items** [refer to list on wiki] | [LINK](https://community.icann.org/display/gnsocouncilmeetings/Action%2BItems) |
| **2 - Issue Scoping** | **- none -** | LINK |
| **3 - Initiation** | **New gTLD Auction Proceeds Drafting Team** | [LINK](#AUCTION) |
| **4 - Working Group** | **Review of All Rights Protection Mechanisms in All gTLDs** PDP (RPM) | [LINK](#UDRP) |
| **4 - Working Group** | **New gTLD Subsequent Procedures PDP** | [LINK](#subrnd_gTLD) |
| **4 - Working Group** | **Next-Generation gTLD Registration Directory Services (RDS) to replace WHOIS** (WHOIS PDP) | [LINK](#WHOIS_PDP) |
| **4 - Working Group** | **GNSO ICANN Meeting Strategy Drafting Team** | [LINK](#meeting) |
| **4 - Working Group** | **Curative Rights Protections for IGO/INGOs PDP** (IGO-INGO-CRP) | [LINK](#IGO_INGO_RPM) |
| **4 - Working Group** | **GNSO Standing Committee on Improvements Implementation** (SCI) | [LINK](#SCI) |
| **4 - Working Group** | **GNSO PDP Improvements Discussion Group** (PDP-IMPR) | [LINK](#PDP_IMPR) |
| **4 - Working Group** | **GAC-GNSO Consultation Group on Early Engagement** (GAC-GNSO-CG) | [LINK](#GAC_GNSO_CG) |
| **4 - Working Group** | **Cross-Community Working Group to develop a Framework of Principles for Future CWGs** (CWG-Principles) | [LINK](#CWG_CWG) |
| **4 - Working Group** | **Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs** (CWG-UCTN) | [LINK](#CWG_UTCN) |
| **4 - Working Group** | **Cross-Community Working Group on Internet Governance** (CWG-IG) | [LINK](#IG) |
|  |  |  |
| **5 – Council Deliberations** | **- none -** | LINK |
| **6 – Board Vote** | **GNSO Review Working Party** (REVIEW) | [LINK](#REVIEW) |
| **6 – Board Vote** | **Privacy & Proxy Services Accreditation Issues PDP (PPSAI)** | [LINK](#PPSAI) |
| **6 – Board Vote** | **Protection of International Organization Names in All gTLDs PDP** (IGO-INGO) | [LINK](#IGO_INGO) |
| **6 – Board Vote** | **Geo Regions Review** (GEO) | [LINK](#GEO) |
| **7 – Implementation** | **Cross Community Working Group on Enhancing ICANN Accountability (WS1)** | [LINK](#CCWG_WS1) |
| **7 – Implementation** | **Translation/Transliteration of gTLD Registration Data PDP** (T&T) | [LINK](#TandT) |
| **7 – Implementation** | **Inter-Registrar Transfer Policy Part C PDP** (IRTP-C) | [LINK](#IRTP_C) |
| **7 – Implementation** | **‘Thick’ WHOIS PDP** (THICK-WHOIS) | [LINK](#THICK_WHOIS) |
| **7 – Implementation** | **Protection of International Organization Names in All gTLDs PDP** (IGO-INGO) | [LINK](#IGO_INGO2) |
| **7 – Implementation**  | **IRTP Part D PDP** (IRTP-D) | [LINK](#IRTP_D) |
| **7 – Implementation** | **Cross Community Working Group to Develop an IANA Stewardship Transition Proposal on Naming Related Functions** | [LINK](#IANA) |
| **Other** | **-none-** | -none- |

Last updated: 5 10 May 2016

This list includes GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| **1 - Issue Identification** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| GNSO Council Action Items - [LINK](https://community.icann.org/display/gnsocouncilmeetings/Action%2BItems) | NA | NA | NA | Refer to most recent action item list for latest status |

| **2 - Issue Scoping** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **- None -**  |  |  |  |  |

| **3 – Initiation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[New gTLD Auction Proceeds Drafting Team](https://community.icann.org/display/NGAPDT/New%2BgTLD%2BAuction%2BProceeds%2BDrafting%2BTeam%2BHome)** Chair: Jonathan Robinson Vice-Chair: Alan GreenbergStaff: M. Konings, D. Tait | 2016-Mar-10 | 2016-Jun-27 | DT | The new gTLD Program established auctions as a mechanism of last resort to resolve string contention. Most string contentions (approximately 90% of sets scheduled for auction) have been resolved through other means before reaching an auction conducted by ICANN's authorized auction service provider, Power Auctions LLC. However, it was recognized from the outset that significant funds could accrue as a result of several auctions. As such, these auction proceeds have been reserved and earmarked until the Board authorizes a plan for the appropriate use of the funds. Board, staff, and community are expected to be working together in designing and participating in the next steps addressing the use of new gTLD auction proceeds. A drafting team composed of representatives of SO/ACs and the Board has been convened to prepare a draft Charter. This group met for the first time on 10 Mar 2016 in Marrakech and aims to complete its work by ICANN 57 in San Juan, on 24 Oct 2016. |

| **4 – Working Group** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[Rights Protection Mechanisms in All gTLDs PDP](https://community.icann.org/display/RARPMRIAGPWG/Review%2Bof%2Ball%2BRights%2BProtection%2BMechanisms%2B%28RPMs%29%2Bin%2Ball%2BgTLDs%2BPDP%2BWorking%2BGroup%2BHome)** **Chair(s):** TBD**Council Liaison and Interim Chair:** Philip CorwinStaff: M. Wong., L. Hoffmann, D. Tait | 2011-Feb-03 | ongoing | WG | On 28 February, the GNSO Council voted to [initiate](http://gnso.icann.org/en/council/resolutions#20160218-3) the PDP and formed a small group to review the draft Charter. The group concluded its work on 25 February and the Council adopted the updated Charter during its face-to-face meeting in Marrakech. Phil Corwin was appointed as Council Liaison and interim Chair. A call for volunteers has been published and the first WG meeting was held on 21 April 2016. Kathy Kleiman, J. Scott Evans, and Phil Corwin have been selected by the WG as co-Chairs and are expected to be confirmed as such by the GNSO Council at the next Council meeting in May. Staff conducted a background webinar on the Charter and the Final Issue Report on 27 April and on 4 May another webinar was held to provide WG participants with an overview of the specificities of the various policies under review. The WG is expected to finalise its work plan by mid-May.  |
| **[New gTLD Subsequent Procedures](https://community.icann.org/display/NGSPP/New%2BgTLD%2BSubsequent%2BProcedures%2BPDP%2BHome) PDP**Chair(s): Stephen Coates, Avri Doria, and Jeff NeumanCouncil Liaison: Paul McGradyStaff: S. Chan, J. Hedlund | 2014-Jun-25 | 2015-Dec | WG | The GNSO Council voted to initiate the PDP during its 17 December meeting, but deferred the vote on a motion to approve the Charter in order to properly account for RPMs related work between this PDP and the anticipated PDP on RPM review. The final Charter was adopted during the 21 January meeting. The WG began its meetings on 22 February, selected Stephen Coates, Avri Doria, and Jeff Neuman as its Co-Chairs, and agreed to meet weekly for 90 minutes. The PDP WG has begun preliminary deliberations on a set of overarching topics, which are expected to serve as the subject matter for the formal request for input from SO/AC/SG/Cs; the WG aims to send solicit these statements ahead of ICANN56 in Helsinki. |
| **[PDP on the next generation gTLD Registration Directory Service to replace WHOIS](https://community.icann.org/display/gTLDRDS/Next-Generation%2BgTLD%2BRegistration%2BDirectory%2BServices%2Bto%2BReplace%2BWhois)**Chair: Chuck GomesVice-Chairs: David Cake, Michele Neylon, Susan KawaguchiCouncil liaison: Stephanie Perrin Staff: M. KoningsThe WG is tasked to provide the GNSO Council with recommendations on the following two questions as part of phase 1: What are the fundamental requirements for gTLD registration data and is a new policy framework and next-generation RDS needed to address these requirements? | 2012-Nov-8 | Ongoing | WG | The WG continues to meet on a weekly basis for 90 minutes. Following the completion of the work of three sub-teams which were tasked to assemble and summarize relevant information related to data elements, purpose and privacy, the working group will now focus on finalising its work plan.  |
| **GNSO ICANN Meeting Strategy Drafting Team**Council Lead:Volker GreimannStaff support: M. Konings, G. de Saint-Gery | 2015-Feb-11 | ICANN55 | DT | In 2015, the GNSO Council formed a drafting team to develop a proposed framework for GNSO related meetings as part of the new ICANN meeting strategy which will go into effect in 2016. The DT developed a draft proposed approach which was shared with other SO/ACs for discussion at ICANN53 in Buenos Aires. Following that meeting [a letter](http://gnso.icann.org/en/correspondence/robinson-to-crocker-14jul15-en.pdf) was sent by Jonathan Robinson on behalf of the GNSO Council to inform the ICANN Board of the progress to date and to request the ICANN Board to share further information concerning its plans. Some further discussions between the different SO/ACs took place during ICANN55 in Dublin and continued in Marrakech. The Board sent a reply on 12 February 2016 (see <http://gnso.icann.org/en/correspondence/crocker-to-bladel-12feb16-en.pdf>). Further SO/AC discussions are now ongoing regarding the schedule for the first Policy Forum (Meeting B) in Helsinki in June in which Donna Austin and Volker Greimann participate as the GNSO Council representatives.  |
| **[Curative Rights Protections for IGO/INGOs](http://community.icann.org/display/gnsoicrpmpdp/) PDP**Chair: Philip Corwin, Petter Rindforth Council Liaison: Susan KawaguchiStaff: M. Wong, S. Chan | 2014-Jun-05 | Ongoing | WG | Based on the recommendation of the IGO-INGO PDP Working Group, the GNSO Council resolved to initiate a PDP and chartered a WG in June 2014. The PDP WG is tasked to explore possible amendments to the Uniform Dispute Resolution Policy (UDRP) and the Uniform Rapid Suspension procedure (URS) so as to enable International Governmental Organizations (IGOs) and International Non-Governmental Organizations (INGOs) to access and use curative rights protection mechanisms. The WG has made considerable progress in its Work Plan and is focusing its attention on IGOs, as it has preliminarily determined that INGOs do not appear to require additional protections. The WG has reached a preliminary conclusion on the issue of standing and is currently discussing jurisdictional immunity for IGOs within the construct of RPMs. At the WG’s request, an external legal expert, Professor Edward Swaine from George Washington University, was engaged to provide a legal opinion on the state of international law on this topic. Professor Swaine provided a preliminary opinion at the end of January, which was reviewed by the co-chairs with a view to providing Professor Swaine with initial feedback. A synopsis document prepared by Prof. Swaine was circulated to the WG and used to facilitate the group’s discussions at ICANN55. On Comment 26 April, Professor Swaine’s final legal opinion was shared with the WG for their consideration.A follow up set of questions was sent to the IGOs on the issue of IGO immunity as well. The WG is currently also anticipating the delivery of a proposal from the small group of NGPC, GAC and IGO representatives that was formed on the topic. It expects to conduct further engagement with the GAC and IGOs upon receipt of the proposal. |
| **[GNSO Standing Committee on Improvements Implementation (SCI)](https://community.icann.org/display/gnsosci/Home)**Chair: Rudi Vansnick Vice-Chair: Anne Aikman-Scalese Council Liaison: Amr ElsadrStaff: J. Hedlund, M. WongThe GNSO Standing Committee on Improvements Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. It is a standing committee of the GNSO Council. | 2011-Apr-07 | Ongoing | SCI | In April 2015 the GNSO Council consented to referring two issue requests to the SCI for consideration. The [first](https://community.icann.org/display/gnsocouncilmeetings/Motions%2B16%2BApril%2B2015) concerned GNSO Council practices for proposing, seconding, and amending motions and the [second](https://community.icann.org/display/gnsocouncilmeetings/Motions%2B16%2BApril%2B2015) concerned the clarifying of the GNSO Operating Procedures regarding the waiver and resubmission of motions. On the latter topic, the SCI reached consensus that the GNSO Operating Procedures are sufficiently clear that the waiver of the 10-day deadline for motions does not apply to resubmitted motions, and sent a letter on 09 October notifying the GNSO Council of its decision. On the first topic the SCI has documented the Council’s current practice in relation to motions (include amendments), thus completing the first step in the Review Request. On 25 April, the SCI completed a Consensus Call on revisions to the GNSO Operating Procedures to document the current Council practice in relation to motions and will submit these revisions for consideration in a Public Comment Forum along with possible revisions relating to Chair/Vice Chair elections. This last topic was referred to the SCI following the Council’s 19 November 2015 meeting, where it approved a further request for the SCI to review Sections 2.2(f) and 2.2(g) of the GNSO Operating Procedures (i.e. GNSO Council Vice-Chairs serving as interim GNSO Chairs, and posting of GNSO Chair election results). On this issue the SCI also is considering possible revisions to the GNSO Operating Procedures. |
| **GNSO PDP Improvements Implementation Discussion Group**Volunteers: Staff: M. Konings, Lars HoffmannThe GNSO Council agreed to form a small committee of interested Council members to work with staff on the implementation of the GNSO PDP Improvements (see <http://gnso.icann.org/en/drafts/pdp-improvements-table-16jan14-en.pdf>), particularly items 3 (Increase pool of PDP volunteers) and 5 (Improved online tools & training) . | 2014-Jan-30 | Ongoing | Council /Staff | The group has been dormant awaiting the development of further initiatives and assessment of further need for consultation by staff.Staff provided a status update on the implementation of the recommendations during the ICANN meeting in Buenos Aires and will continue to move forward with the implementation of the previously identified GNSO PDP improvements, incorporating the suggestions made.Following very helpful feedback from the Community, Staff completed the GNSO Learn module and presented it to the GNSO in Dublin. The [course is live](http://learn.icann.org/courses/gnso) and a social media campaign to promote was launched in November 2015. |
| **[GAC-GNSO Consultation Group on GAC Early Engagement in GNSO PDP](https://community.icann.org/x/phPRAg)s**Chairs: Jonathan Robinson (GNSO) and Manal Ismail (GAC)Staff: M. Konings, O. NordlingThe Governmental Advisory Committee (GAC) and the Generic Names Supporting Organization (GNSO) have jointly established a consultation group to explore ways for the GAC to engage early in the GNSO Policy Development Process (PDP) and to improve overall cooperation between the two bodies (for example, by exploring the option of a liaison). | 2014-Jan-07 | Ongoing | CG | The launch of this GAC-GNSO Consultation Group on Early Engagement is the result of discussions between the two entities at the ICANN meeting in Buenos Aires as well as previous ICANN meetings, reflecting a joint desire to explore and enhance ways of early engagement in relation to GNSO policy development activities. The issue was also specifically called-out by both Accountability and Transparency Review Teams (ATRT). The CG reconvened following the ICANN meeting in Dublin and has now completed its work on the review of the GNSO Liaison to the GAC, the review of the Quick Look Mechanism and has shared initial ideas concerning other opportunities for early engagement of the GAC in the GNSO PDP. The GNSO Council confirmed during its last meeting that the position of GNSO Liaison to the GAC should be made a permanent role. The CG is developing a survey which is aimed to obtain further input from the GNSO as well as GAC on the review of the Quick Look Mechanism as well as other opportunities for early engagement of the GAC in the GNSO PDP.  |
| **[Cross-Community Working Group- on a Framework of CWG Principles](https://community.icann.org/x/rQbPAQ)**GNSO Council Co-Chair: John BerardccNSO Council Co-Chair: Becky BurrStaff: M. Wong, B. Boswinkel, S. ChanThe CCWG was chartered by the ccNSO and GNSO Councils to develop a set of uniform guidelines (based on earlier work by the GNSO, feedback from the ccNSO and community experience from past CCWGs) for the formation, operation and termination of future cross-community working groups. | 2011-May-19 | Ongoing | CWG | This Cross-Community Working Group was chartered by both the ccNSO and GNSO Councils in March 2014. The CCWG has reviewed the processes and outcomes of selected prior CWGs, including mapping their charters to the typical WG life cycle (Initiation, Formation, Operation, Closure, Post-Closure). As a result of the recent further usage of new CCWGs, the co-chairs and staff prepared a preliminary draft checklist for all the various stages of the WG life cycle, which was shared with the community at the Buenos Aires meeting. A more complete draft framework was prepared following additional CWG discussion and published for public comment on 22 February 2016. The initial 40-day comment period was extended by request of the CWG co-chairs following discussions in Marrakech: <https://www.icann.org/public-comments/ccwg-framework-principles-draft-2016-02-22-en>. The CWG co-chairs have also sought specific input on the draft Framework from other SO/ACs and the ICANN Board. A final proposed framework is expected to be prepared following the close of the public comment period and circulated in time for community deliberation at ICANN56. |
| **[Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs (CWG-UCTN)](https://community.icann.org/x/X7XhAg)**GNSO Council Co-Chairs: Heather Forrest, Carlos Gutierrez ccNSO Council Co-Chairs: Paul Szyndler, Annabeth LangeCouncil liaison: Heather ForrestStaff: M. Konings, B. Boswinkel, Lars Hoffmann* The objective of the CWG is to: Further review the current status of representations of country and territory names, as they exist under current ICANN policies, guidelines and procedures;
* Provide advice regarding the feasibility of developing a consistent and uniform definitional framework that could be applicable across the respective SO’s and AC’s; and
* Should such a framework be deemed feasible, provide detailed advice as to the content of the framework.
 | 2014-Mar-26 | Ongoing | CWG | The CWG is using an Options Paper to drive forward its discussion and has just concluded its work on two-letter codes. Following a request for input that was sent to all SO/ACs and SG/Cs on 3-character codes, the co-Chairs requested that Staff draft a straw person proposal on 3-character codes that was presented and discussed during ICANN55. The Group has resumed its discussion on 11 April. Communication channels with the GAC remain open regarding potentially overlapping work efforts, and the GAC invited the CWG-UCTN co-Chairs to meet during ICANN56. |
| **[Cross-Community Working Group on Internet Governance (CCWG-IG)](https://community.icann.org/pages/viewpage.action?pageId=43984275)**Co-Chairs: Rafik Damak (GNSO), Jordan Carter (ccNSO), Olivier Crepin-Leblond (ALAC)GNSO Council Liaison: Carlos GutierrezStaff: A-R Inne, N. Hickson, R. DewulfThe Internet Governance CWG has been established by the participating SO’s and AC’s to coordinate, facilitate, and increase the participation of the ICANN community in discussions and processes pertaining to Internet Governance.  | 2014-Oct-15 | Ongoing | CCWG | The GNSO Council adopted the charter for this CCWG during ICANN51. The CCWG requested confirmation from its Chartering Organizations regarding a question of interpretation of its charter, which the GNSO Council agreed to at its May 2015 meeting. The CCWG co-chairs provided an update to the ccNSO and GNSO Councils at ICANN55. The GNSO Council is expected to review the status of this CWG in further detail during its upcoming meeting. |

| **5 – Council Deliberation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **- none -** |  |  |  |  |
|  |  |  |  |  |

| **6 – Board Vote** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[GNSO Review Working Party](https://community.icann.org/x/OJLhAg)**Lead: Jennifer WolfeStaff: M. Konings, M. WongFollowing discussions in Singapore, the GNSO Council agreed to form a small committee to liaise with the Board’s Structural Improvements Committee (now the Organizational Effectiveness Committee (OEC)) on the GNSO Review and discuss a potential self-review of the GNSO Council. | 2014-Apr-07 | Ongoing | Working Party / Council | The Initial Report by Westlake, the independent examiner selected by the Board’s Organizational Effectiveness Committee (OEC), was published for public comment on 1 June, with the comment period closing on 24 July 2015. A final report was published on 15 September: <https://www.icann.org/news/announcement-2-2015-09-15-en>. The GNSO Review Working Party has finalized its feedback on the final report (intended to inform the OEC and Board’s further actions on this matter) and has completed an Implementability and Prioritization Analysis of the recommendations. This was submitted to the GNSO Council for its consideration in Marrakech. The Council deferred its vote on the matter to allow SG/Cs further time to review the analysis document. At its April meeting, the Council voted to adopt the Working Party’s analysis. The result of the Council’s vote, the Working Party’s analysis and further background material have been forwarded to the OEC for its consideration at the Board meeting in May.  |
| **[Privacy & Proxy Services Accreditation Issues PDP WG](https://community.icann.org/pages/viewpage.action?pageId=43983094)** Chair: Don BlumenthalVice-Chairs: Graeme Bunton, Steve MetalitzCouncil Liaison: James BladelStaff: M. Wong, M. Konings The *Registrar Accreditation Agreement* (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which were identified as those relating to privacy & proxy services and their accreditation, were to be examined in this PDP. | 2009-May-21 | Ongoing | Board | The WG’s Initial Report was published for public comment on 5 May: see <https://www.icann.org/public-comments/ppsai-initial-2015-05-05-en>, and closed on 7 July. Due to the volume of comments, the WG created four Sub Teams to facilitate review of the comments, and revised its timeline for completion of its Final Report. It also held a face to face meeting at ICANN54 to facilitate its task. The Final Report was sent to the GNSO Council on 8 December 2015 (see [http://gnso.icann.org/en/issues/raa/ppsai-final-07dec15-en.pdf)](http://gnso.icann.org/en/issues/raa/ppsai-final-07dec15-en.pdf%29). The Council agreed to defer a vote on the report to its 21 January 2016 meeting, to allow all SG/Cs sufficient time to consider the final recommendations from the WG. At the 21 January meeting, the GNSO Council voted unanimously to approve all the WG’s final recommendations. A public comment forum was opened to allow the public to comment (through 16 March) on the recommendations prior to Board action, as required by the ICANN Bylaws: see <https://www.icann.org/public-comments/ppsai-recommendations-2016-02-05-en>. As further required by the Bylaws, the Council [approved](http://gnso.icann.org/en/meetings/minutes-council-18feb16-en.htm) a Recommendations Report for transmission to the ICANN Board at its 18 February meeting. The Recommendations Report has been forwarded to the Board for its review at its May 2016 meeting. The WG Vice-Chairs met with representatives of the GAC’s Public Safety Working Group in Marrakech to discuss the GAC’s concerns with the final recommendations. |
| **[Protection of International Organization Names in All gTLDs](http://gnso.icann.org/en/group-activities/active/igo-ingo) PDP**Staff**:** M. Wong, Steve Chan, Berry CobbChair**:** Thomas Rickert | 2012-Apr-12 | 2014-Dec-11 | Board/Council/IRT | The GNSO Council unanimously approved the IGO-INGO WG’s consensus recommendations at its 20 Nov 2013 meeting. As requested by the Board, the NGPC developed a proposal taking into account the GNSO’s recommendations and GAC advice in March 2014. In April 2014 the Board voted to adopt those of the GNSO’s recommendations that are not inconsistent with GAC advice received on the topic. Staff has organized an Implementation Review Team (in line with the GNSO’s recommendation), led by Fabien Betremieux, to implement those recommendations adopted by the Board (See below in the “7 – Implementation” section for more details). A Call for Volunteers to the IRT was issued following the Buenos Aires meeting and the IRT held its first meeting in late September. It met again in Dublin and reconvened in late January 2016 following further staff work on a proposed implementation plan. The IRT also met in Marrakech to discuss progress on the implementation plan.On 18 June 2014 the NGPC sent a letter to the GNSO Council requesting that the GNSO contemplate initiating a process to consider possible modifications to its remaining recommendations, per the PDP Manual. The GNSO Council held a discussion with Chris Disspain at its 5 September meeting and sent a [letter](http://gnso.icann.org/en/correspondence/robinson-to-chalaby-disspain-07oct14-en.pdf) on 7 Oct 2014 to the NGPC seeking confirmation and input about the most appropriate forms of protection for IGO acronyms and Red Cross names. At the ICANN51 meeting the NGPC adopted a resolution to temporarily reserve the Red Cross National Society identifiers until the differences between the GNSO recommendations and the GAC Advice have been reconciled. Staff is currently working on implementing this resolution, with assistance from the Red Cross. A response from the NGPC to the Council’s letter was received on 15 January 2015 noting that discussions are ongoing. An updated proposal for IGO protetions being developed by a small group of IGO, GAC and NGPC representatives is expected to be delivered to the GNSO for consideration following ICANN55. Representatives from the Red Cross provided a briefing to the Council during the Council’s April meeting, and the Council is discussing sending a letter to the Board requesting specific Board input as a follow up. The Council is likely to await further and more definite information from the NGPC before taking any further action on either topic. |
| **[Geo Regions Review Community-wide Working Group](https://community.icann.org/display/georegionwg/Home%2BPage%2Bof%2BGeographic%2BRegions%2BReview%2BWorking%2BGroup)**Chair: Cheryl Langdon-Orr (ccNSO/APRALO)GNSO Council Reps: Staff: R. HoggarthThis Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions.  | 2008-Aug-07 | April 2016 | Board | A community Public Comment opportunity has been established for this matter (see <https://www.icann.org/public-comments/geo-regions-2015-12-23-en>. The comment period closed on 24 April 2016 and 7 submissions were received. The staff report of public comments is expected to be published by 9 May. |

| **7 – Implementation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[Cross Community Working Group on Enhancing ICANN Accountability](https://community.icann.org/x/ogDxAg)**Co-Chairs: Mathieu Weill (ccNSO), Thomas Rickert (GNSO), Leon Sanchez (ALAC)Staff support: G. Abuhamad, A. Jansen | 2014-Oct-16 | Ongoing | CCWG/Council | The GNSO Council approved the CCWG [Charter](http://gnso.icann.org/en/council/resolutions#20141113-1) at its November 2014 meeting. The charter was also approved by the ccNSO, GAC and ALAC, in addition to the GNSO. The CCWG has a near-term focus of collecting current and possible future accountability mechanisms to be assigned in Work Streams 1 & 2, with WS1 being considered the more urgent accountability mechanisms required for the IANA Stewardship transition to take place. The CCWG formed three Work Parties to further develop Community Powers, Accountability Mechanisms, and Stress Tests. Legal advisors were engaged to assist the CCWG as well. After review of the public comments on the first version of the WS1 proposal, face to face sessions at ICANN53 and a subsequent face to face meeting in Paris, the CCWG launched a [second public comment period](https://www.icann.org/public-comments/ccwg-accountability-2015-08-03-en) based on the proposed single member community mechanism on 3 Aug 2015, closing on 12 Sept 2015. Additionally, the ICANN Board submitted its comments regarding a multi-stakeholder model for the CCWG to consider. Following sessions in Dublin, the CCWG co-chairs issued a preliminary summary on 15 November and the full Third Draft Proposal was published on 30 November, with public comments closing on 21 December. SO/AC Chartering Organizations were requested to consider whether to approve the proposal as early as possible, and the GNSO Council scheduled a Special Session on 14 January 2016 to discuss its response to the CCWG. The Council finalized its response at its 21 January meeting. In February, the CCWG released its Supplemental Final Proposal, having considered feedback from all its Chartering Organizations. The CCWG’s Chartering Organizations approved this Supplemental Final Proposal at ICANN55 in Marrakech. The CCWG is now discussing implementation of its WS1 recommendations, and preparing to commence work on WS2.  |
| **[Translation/Transliteration of Internationalized Registration Data PDP](https://community.icann.org/display/tatcipdp/Translation%2Band%2BTransliteration%2Bof%2BContact%2BInformation%2BPDP%2BHome)**  | 2012-Oct-17 | Ongoing | Staff | On 28 September the ICANN Board [passed the motion](https://www.icann.org/resources/board-material/resolutions-2015-09-28-en) to adopt all seven recommendations contained in the Final Report. GDD Staff believes it may be useful to join the forthcoming T&T IRT and the existing Thick Whois IRT. T&T co-Chairs have been contacted about this possibility and staff will also reach out to the GNSO in due course to assure the Council approves such a move. A draft implementation plan and a call for volunteers to joining the Implementation Review Team will be send out as soon as the IRT methodology is agreed upon. |
| **IRTP Part C Recommendations** The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see <http://gnso.icann.org/en/resolutions#20121017-4>).  | 17 Oct 2012 | 1 Sept 2015 | Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December 2012 (see <https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a>). As instructed by the GNSO Council, an Implementation Review Team was formed. Meetings of the IRT have recommenced and details of the proposed implementation plan have been shared with the IRT. Staff sought input from the IRT on the Change of Registrant draft policy language, and the draft policy was posted for public comment on 30 March 2015. Comments were due 16 May 2015, and the IRT reviewed the comments received. The updated Transfer Policy was announced on 24 September 2015 (see <https://www.icann.org/news/announcement-2-2015-09-24-en>). The updated Transfer Policy will be effective for all ICANN-accredited registrars 1 August 2016. |
| **Thick WHOIS PDP Recommendations**The GNSO Council adopted the recommendation to require Thick Whois for all gTLD registries at its meeting on 31 October 2013. Council Liaison: Amr Elsadr | 2012-Mar-14 | Ongoing | Staff | The ICANN Board approved the GNSO recommendations on Thick Whois at its meeting on 7 February 2014. (<http://www.icann.org/en/groups/board/documents/resolutions-07feb14-en.htm>). An Implementation Review Team has been formed and various impact assessments and implementation proposals have been discussed with the IRT in the two decoupled work streams, corresponding to the two expected outcomes in the PDP Recommendations: transition from thin to thick for .COM, .NET and .JOBS; and the consistent labeling and display of Whois output for all gTLDs as per Specification 3 of the 2013 RAA. Further discussions of the proposals, issues, and risks are being planned in subsequent IRT sessions. Regarding the transition from thin to thick for .COM, .NET and .JOBS, in June 2015, ICANN’s General Counsel’s Office, released to the IRT a Legal Review Memorandum per the GNSO Council’s recommendation. ICANN Staff is currently engaging with experts from affected parties to identify an implementation path.Regarding the Consistent Labeling and Display of Whois output for all gTLDs, ICANN Staff, in conjunction with the IRT, has developed a Draft Consensus Policy which was submitted to the Community in a Public Comment period closed on 18 April 2016. ICANN Staff is currently considering community input in collaboration with the IRT. |
| **Protection of International Organization Names in All gTLDs** The GNSO Council adopted the recommendation to protect certain identifiers of IGO & INGO Organizations in all gTLD registries at its meeting on 20 November 2013. | 2012-Apr-12 | Ongoing | Staff/IRT  | The GNSO Council unanimously approved the IGO-INGO WG’s consensus recommendations at its 20 Nov 2013 meeting. In April 2014 the Board voted to adopt those of the GNSO’s recommendations that are not inconsistent with GAC advice received on the topic. Staff has formed an Implementation Review Team (in line with the GNSO’s recommendation) to implement those recommendations adopted by the Board.To date, ICANN Staff has been working on building comprehensive and actionable lists of all the identifiers to be protected as well as draft procedures for eventual implementation of relevant protections: reservations at the top and second levels and related exception procedures. Staff, in collaboration with the IRT, is progressively building a Draft Consensus Policy document. This document serves to support the continuing development of the implementation plan. |
| [**IRTP Part D PDP WG**](https://community.icann.org/display/ITPIPDWG/Inter-Registrar%2BTransfer%2BPolicy%2B%28IRTP%29%2BPart%2BD%2BWorking%2BGroup%2BHome)* The GNSO Council unanimously adopted the recommendations of the IRTP Part D PDP at its meeting on 15 October 2014 (see http://gnso.icann.org/en/council/resolutions#20141015-1).
 | 2012-Oct-17 | Ongoing | Staff | The ICANN Board approved the GNSO recommendations of IRTP D on 12 February 2015 (https://www.icann.org/resources/board-material/resolutions-2015-02-12-en#1.d). GDD staff has drafted an Implementation Plan and the Implementation Review Team (IRT) has been meeting on a biweekly basis since August. The draft Transfer Dispute Resolution Policy (TDRP) and draft Transfer Policy were posted for public comment on 10 November 2015. The comment period closes 21 December 2015. The IRT has reviewed all of the comments, and Staff is working on website and educational material updates per the public comments received. No comments were received regarding the draft TDRP and Transfer Policy. The projected effective date is 1 August 2016. |
| **[Cross Community Working Group to Develop an IANA Stewardship Transfer Proposal on naming related functions](https://community.icann.org/display/gnsocwgdtstwrdshp/CWG%2BDrafting%2BTeam%2Bon%2BStewardship%2BTransition%2BHome)**Co-Chairs: Jonathan Robinson (GNSO), Lise Fuhr (ccNSO)Council Liaison: Jonathan RobinsonStaff: M. Konings, B. Boswinkel, G. AbuhamadThis CWG was formed to develop an IANA Stewardship Transfer Proposal on naming related functions. | 2014-Jul-14  | Ongoing | ICG/CWG | The CWG delivered the final proposal for SO/AC consideration on 11 June. The GNSO Council, in addition to all other chartering organization approved the CWG’s names proposal during the ICANN 53 meeting in Buenos Aires. As a result, the CWG submitted the names related proposal to the ICG. The ICG has published the proposal to transition the stewardship of the IANA functions, which integrates the proposals of all three operational communities, for public comment from July 31 to September 8 (see https://www.ianacg.org/calls-for-input/combined-proposal-public-comment-period/). The CWG was awaiting the outcomes of the CCWG given the documented dependencies related to any changes to ICANN’s accountability framework and continued to meet every two weeks to address issues in relation to the implementation of the IPR, budget recommendations and Bylaw changes as a result of the CWG-Stewardship recommendations. Following the issuance of the Supplemental Final Proposal by the CCWG-Accountability, the CWG has since confirmed that the CCWG-Accountability’s final recommendations meet the requirements it had set forth in its proposal: see <https://gnso.icann.org/mailing-lists/archives/council/pdf5EOLDCNvkO.pdf>.  |