|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Event** | **Action/Decision** | **Who** |
| **November 15** | Summary report with recommendations and summary of changes distributed to SO/AC | Advise the GNSO on items that will require specific attention and/or review | GNSO CCWG members |
| **November 15** | Beginning of Public Comment period | Start preparation of GNSO draft comment | GNSO CCWG members |
| **November 15** | Communication from CCWG-Accountability Chairs to Chartering Organization |  | CCWG-Accountability Chairs |
| **November 19** | GNSO Council Meeting  (teleconference) | Update on 3rd draft proposal | Thomas Rickert, GNSO CCWG members |
| **November 30** | Publication of full 3rd draft CCWG Proposal | Share detailed report with Council | GNSO Secretariat |
| **December 5** | Share draft GNSO comment on 3rd draft CCWG Proposal with the Council |  | GNSO CCWG members |
| **December 7** | Document and motion deadline | Submit motion for the approval of the CCWG-Accountability 3rd draft CCWG Proposal |  |
| **December 17** | GNSO Council meeting (teleconference) | Consider the approval of the CCWG-Accountability 3rd CCWG Proposal  Review and adoption of GNSO statement on 3rd draft CCWG Proposal | GNSO Council |
| **December 18** |  | Submit GNSO Statement to public comment forum | GNSO Leadership / GNSO Secretariat |
| **December 21** | Deadline for public comments on 3rd draft CCWG Proposal |  |  |
| **?** | CCWG confirms that 3rd draft CCWG Proposal = Final Proposal or submits updated Final Proposal |  | CCWG-Accountability |
| **January 4 or 11 (TBC)** | Document and motion deadline | Submit motion for the approval of the CCWG-Accountability Final Proposal (if this has changed from the 3rd draft) |  |
| **January 14 or 21 (TBC)** | GNSO Council Meeting (teleconference) | Consider motion for the approval of the CCWG-Accountability Final Proposal (if this has changed from the 3rd draft) |  |