TABLE OF CONTENTS (click on the link below to go directly to the project in this list).

Projects are listed in the order in which they were initiated.

| GNSO Working Groups / Drafting Teams | Abbreviation |
| --- | --- |
| GNSO Improvements Standing Committee on Improvement Implementation | SCI |
| Synthesis of WHOIS Service Requirements – Survey Working Group | WHO2 |
| Drafting Team on Cross-Community Working Groups | CWG-DT |
| Fake Renewal Notices Drafting Team | FRN-DT |
| Locking of a domain name subject to UDRP proceedings |  |
| Protection of Intergovernmental Organization Names in All gTLDs | IGO-INGO |
| ‘Thick’ WHOIS PDP Working Group | Thick WHOIS |
| IRTP Part D PDP Working Group | IRTP Part D |
| Policy & Implementation DT |  |
| GNSO Metrics & Reporting WG (Uniformity of Reporting) | MetRep |

| Other GNSO Activities | Abbreviation |
| --- | --- |
| WHOIS Studies | WHO1 |
| Registrar Accreditation Agreement | RAA |
| Defensive Registrations | DefRg |
| Uniform Dispute Resolution Policy (COMPLETED FOR NOW) | UDRP |
| Translation/Transliteration of Internationalized Registration Data |  |
| Purpose of Whois Issue Report | Whois PDP |

| Joint SO/AC Working Groups | Abbreviation |
| --- | --- |
| Geo Regions Review Community-wide Working Group | GEO |
| Joint ccNSO-GNSO Internationalized Domain Names Working Group (JIG) | JIG |
| Joint Security and Stability Analysis Community Drafting Group (DNS Cert) | DSSA |
| ccNSO Study Group on the Use of Names for Countries and Territories | NCTSG |

| Approved GNSO PDP Recommendations | Abbreviation |
| --- | --- |
| IRTP Part B Adopted Recommendations | IRTP Part B |
| Inter-Registrar Transfer Policy Part C PDP | IRTP Part C |

| Outstanding Recommendations for Council Action | Abbreviation |
| --- | --- |

Last updated: 3 July 2013

This list includes pending GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| GNSO Working Groups / Work Teams / Drafting Teams |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| GNSO Standing Committee on Improvements Implementation (SCI) Chair: Ron Andruff Vice-Chair: Avri Doria Staff: J. Hedlund, M. Konings The GNSO Standing Committee on Improvement Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. | 2011-Apr-07 | Ongoing | SCI | The SCI is working on the following topics: - Drafting Team to modify the SCI charter - Working Group Survey; - Re-submitting a motion. The SCI is now meeting monthly. Recent recommendations that were approved by the Council and included in revised GNSO Operating Procedures include changes to the PDP Manual to address suspension and termination of a PDP. |
| Synthesis of WHOIS Service Requirements – Survey Working Group Chair: Michael Young Staff: B. Cobb Liaison: Wendy Seltzer In May 2009 the GNSO Council asked staff to collect and organize a comprehensive list of potential WHOIS service requirements, based on current policies and previous policy discussions. See: http://gnso.icann.org/issues/whois/whois-service-requirements-final-report-29jul10-en.pdf This report was completed in 2010 and in May 2011 the GNSO Council created a WG to develop a survey to estimate the level of agreement that the conclusions and assumptions in the Inventory Report have in the community. | 2009 May-7 | Ongoing | Staff | The WG closed the survey on 31 October 2012 with 67 complete submissions. ICANN Staff has compiled and condensed the results by each survey section and produced a draft Final Report for WG review. Upon approval of the report by the Working Group, the Final report will be sent to the GNSO Council for their consideration. |
| Drafting Team on Cross-Community Working Groups Discussion leader: J. Robinson Staff: J. Hedlund A drafting team was formed to develop an approach with respect to cross-community working groups. | 19 May 2011 | Ongoing | Council | A public session was held in Prague during which it was suggested that the next step should be to solicit support from interested SO and AC Chairs to suggest volunteers for a CWG to develop revised principles. Staff sent a request for volunteers to the SO and AC chairs, but only SSAC and ccNSO put forward volunteers. The GNSO Council sent a letter to the ccNSO requesting their changes / edits to the proposed principles which then can be reviewed and discussed with the GNSO and others interested. The ccNSO sent a response on 28 June that the GNSO is expected to review in Durban. |
| Fake Renewal Notices Drafting Team (FRN-DT) Chair: Mike O’Connor Staff: M. Konings The GNSO Council requested that a small group prepare a request for information concerning Fake Renewal Notices for the RrSG to help inform its deliberations on the RAP WG Recommendation on Fake Renewal Notices (#2). | 2011-Oct-06 | Ongoing | RrSG / Mason Cole | At its meeting in July, the GNSO Council considered the report of the Fake Renewal Notices DT (see http://gnso.icann.org/issues/frn/fake-renewal-notices-updated-report-20jun12-en.pdf). On the recommendation of the RrSG, a number of alternative approaches are now being pursued to address this issue, including working with ICANN Compliance, reaching out to the relevant local authorities and considering whether it would be appropriate to address this as part of the RAA negotations. Mason Cole provided a status updata by email in February (see http://gnso.icann.org/mailing-lists/archives/council/msg14235.html). |
| Protection of Intergovernmental Organization Names in New gTLDs Staff: B. Peck, B. Cobb Chair: Thomas Rickert Council Liaison: Jeff Neuman | April 2012 | Ongoing | WG | The GNSO Council approved the motion to commence a PDP at the Toronto Meeting and adopted the WG Charter at its November 2012 meeting. The WG published its Initial Report and opened a public comment period on 14 June 2013 to solicit Community feedback on the policy recommendation options the WG is currently considering. The WG will host a face to face session at the Durban Meeting on 15 July; and support a public discussion session on 17 July. |
| Locking of a Domain Name subject to UDRP Proceedings PDP Working Group Chairs: Michele Neylon (Chair), Alan Greenberg (Vice-Chair) Council Liaison: Joy Liddicoat Staff: M. Konings, B. Cobb The GNSO Council approved the charter for the PDP WG on the requirement to lock a domain name subject to UDRP proceedings at its meeting in Costa Rica. The WG is tasked to address the locking of a domain name subject to Uniform Dispute Resolution Policy (UDRP) proceedings. | 15 Dec 2011 | Ongoing | WG | The WG published its Initial Report and opened a public comment forum on 15 March 2013. The initial comment period closed on 26 April 2013, which has been followed by the reply period which closed on 17 May 2013. The WG has reviewed the comments received and is expected to publish its Final Report in time for GNSO Council consideration in Durban. |
| ‘Thick’ WHOIS PDP WG Chairs: Mikey O’Connor Council Liaison: Volker Greimann Staff: M. Konings, B. Cobb As recommended by the IRTP Part B Working Group, the GNSO Council requested ICANN Staff to prepare an Issue Report on the requirement of ‘thick’ WHOIS for all incumbent gTLDs. At its meeting in Costa Rica, the GNSO Council initiated the PDP. | Nov 2012 | Ongoing | WG | The WG has published its Initial Report for Public Comment on 21 June 2013. Comments may be submitted until 14 July, followed by a reply period which will close on 4 August. Upon conclusion of the public comment period, the WG will review all comments received and incorporate any approved changes in the Final Report. The WG will present the findings from the Initial Report during a public session in Durban on Wednesday, 17 July. |
| IRTP Part D PDP WG Co-Chair: James Bladel, Mikey O’Connor Council Liaison: Volker Greimann Staff: L. Hoffmann, M. Konings. PDP on the remaining IRTP issues which include: - Reporting requirements for registries and dispute providers in relation to the TDRP; - How to handle disputes when multiple transfers have occurred in the TDRP; - Should dispute options for registrants be developed; - Should there be requirements or best practices for registrars to make information on transfer dispute resolution options available; - Are existing penalties for policy violations sufficient; - Have EPP AuthInfo codes eliminated the need for FOAs. | 17 Oct 2012 | Ongoing | WG | The WG held its first meeting on 25 February and will continue to meet on a weekly basis. The WG reached out to the community and has finished reviewing the received input. The WG is now in the process of drafting its initial recommendations and will continue its substantive works especially with regard to assessing possible changes to the TDRP. The goal for the publication of the Initial Report is currently set for August 2013. |
| Policy & Implementation Drafting Team Chair: TBC Staff: M. Konings The GNSO Council agreed in Beijing to form a DT to develop a Charter for a Working Group to address issues that have been raised in the context of the recent discussions on policy & implementation that affect the GNSO. | 9 May 2013 | Ongoing | DT | The DT is in the process of finalizing its work on the charter and expects to submit it to the GNSO Council in time for consideration in Durban. |
| GNSO Metrics & Reporting WG (Uniformity of Reporting) Chair: TBC Staff: B. Cobb, M. Konings Request for an Issue Report on the Uniformity of Reporting following a recommendation from the Registration Abuse Policies Working Group (RAPWG) | 17 Oct 2012 | Ongoing | Staff | At its May 2013 meeting, The GNSO Council approved a motion to await the completion of ICANN’s Contractual Compliance three-year plan before determining if any policy development will be required with respect to metrics and reporting of the compliance function. In the meantime, the Council also approved the formation of a Drafting Team to develop a charter for a non-PDP Working Group to consider additional methods for collecting necessary metrics and reporting from Contracted Parties and other external resources to aid the investigation. A “Call for Volunteers” announcement was circulated early June to begin the initiation of this DT. To date, only four community members have volunteered for this effort and this issue will be discussed in Durban. |

| Other GNSO Activities |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| STUDIES |  |  |  |  |
| WHOIS Studies Staff: B Roseman, Mary Wong The GNSO Council has approved studies of WHOIS. Topics include Misuse of WHOIS Data, Registrant Identification Information, Proxy and Privacy “Abuse” and Proxy and Privacy “Relay” and “Reveal”. Budget has been approved by the ICANN Board for these studies. | 2007 Oct-31 | Ongoing | Staff | Staff is overseeing four studies of WHOIS as requested by the GNSO which are now nearing completion: - A study of misuse of public gTLD WHOIS data – CMU is conducting the study with results expected mid-year 2013. They are preparing a draft of their initial stage of data which should be available for public comment shortly following the July ICANN Durban meeting. A webinar will be scheduled in August for their initial findings; - A Registrant Identification Study –launched in October 2011, with draft analysis by NORC. A webinar with summary findings was held on 6 March. The Final Report has been published:. - A year-long Proxy/ Privacy “Abuse” Study –National Physical Lab of the UK is conducting this study and results are expected mid-year 2013. Their draft report will likely be posted for public comment in the third quarter of 2013. - A pre-study “survey” on Proxy/Privacy “Relay” and “Reveal” – final report [PDF, 1.23MB] has been published and this study is now completed. |

| AWAITING COUNCIL ACTION |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| RAA Staff: M. Konings; B. Peck The Registrar Accreditation Agreement (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board approved a first set of amendments, intended to provide clarity and certainty regarding the duties of registrars and rights of registrants, in May, 2009. A Working Group then developed a “charter of registrants’ rights” and a report of other possible RAA amendments, posted at: http://gnso.icann.org/issues/raa/raa-improvements-proposal-final-report-18oct01-en.pdf | 2009 May-21 | Ongoing | Staff Report on the Closing of the Negotiations | A Final Issue Report was published prior to Costa Rica, recommending that the Board requested PDP not commence until after the negotiations were concluded, and the “remaining items” that remain unaddressed are identified. These remaining items would become the subject of one or more PDPs. The Reply Period of the Public Comment Forum for the proposed 2013 RAA closed on 4 June (see http://www.icann.org/en/resources/registrars/raa/proposed-agreement-22apr13-en.pdf); and the ICANN Board approved the new 2013 RAA on 28 June. (see http://www.icann.org/en/resources/registrars/raa/approved-with-specs-27jun13-en.pdf) Staff is currently preparing a briefing paper outlining the background, current status and possible next steps related to initiating the PDP on this topic as part of the RAA PDP. |
| Translation/Transliteration of Internationalized Registration Data. Staff: J. Hedlund/S. Sheng | 17 Oct 2012 | 13 June 2013 | Council | In Toronto, the GNSO Council approved the IRD-WG’s Final Report recommendations and requested staff to complete an Issue Report on recommendation 2, relating to the translation and transliteration of contact information. The Preliminary Issue Report was published for public comment on 08 Jan and the Final Issue Report was submitted to the Council on 21 March. The Council had an initial exchange of view on the Final Issue Report in Beijing and decided at its meeting on 16 May to defer consideration of a motion to initiate a PDP to its meeting on 13 June.approved the initiation of a PDP on these issues at its meeting on 13 June. Staff issued a call for volunteers for a charter drafting team on 18 June and a first meeting is scheduled in Durban on 15 July. |
| Defensive Registrations in New GTLDs: The New GTLD Committee requests the GNSO to consider whether additional work on defensive registrations at the second level should be undertaken. Staff: Brian Peck | 4 June 2012 |  | Council | Staff has delivered a briefing paper http://gnso.icann.org/en/node/32287 and an update presentation to the GNSO Council on the topic of defensive registrations at the second level in response from a request from the New GLTD Committee (2012.04.10.NG2). The Council had an initial discussion on this item at its December meeting and is expected to continue its deliberations at future meetings. This issue is also closely linked to the BC/IPC Proposal for a limited defensive registrations mechanism and the TMCH Strawman proposal. The Council sent a response letter regarding the TMCH Strawman proposal to the CEO on 28 February 2013. No formal decision has been made on whether further Council deliberations on this issue are warranted. |

| Staff Implementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Issue Report on the purpose of collecting and maintaining gTLD registration data and on solutions to improve accuracy and access to gTLD registration data. Staff: L. Hoffmann, M. Wong | 2012-Nov-8 |  | Staff | The Board resolution on the Whois RT Recommendations (see http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm) directs preparation of an Issue Report on the purpose of collecting and maintaining gTLD registration data, and on solutions to improve accuracy and access to gTLD registration data, as part of a Board-initiated GNSO policy development process. The Preliminary Issue Report was published for public comment on 15 March 2013. The comment forum closed on 13 May. A Final Issue Report will be published following the finalization of the EWG recommendations. |
| INACTIVE PROJECTS |  |  |  |  |
| Uniform Dispute Resolution Policy Issue Report Staff: Request for an Issue Report on the current state of the UDRP. | 2011-Feb-03 | Completed for now |  | The GNSO Council deferred commencement of a PDP, except with regard to the lock issue. An Issue Report to be delivered eighteen months after the first delegation of new gTLDS. |

| Joint SO/AC Working Groups |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Geo Regions Review Community-wide Working Group Chair: Dave Archbold (ccNSO) GNSO Council Reps: Zahid Jamil and Ching Chiao Staff: R. Hoggarth This Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions. Changes could have broad impact, so this WG has representatives from most SOs and ACs. Working Group Wiki Page Link | 2008 Aug-07 | 17 October 2013 | Community | The Working Group has published its Final Report recommendations (see - http://www.icann.org/en/news/announcements/announcement-22jun13-en.htm) T he Final Report will soon be formally circulated to all ICANN SOs and ACs (including the Council) for review and comment. Comments will be due no less than 90 days after the conclusion of the ICANN Public Meeting in Durban (17 October 2013). |
| Joint ccNSO-GNSO IDN Working Group (JIG) ccNSO Co-chair: J. Zhang GNSO Co-chair: E. Chung Staff: B. Boswinkel, S. Sheng This group identified three IDN issues of common interest and is proposing ways to resolve them: 1) Single character IDN ccTLDs and gTLDs; 2) aspects of variant management in the root zone; and 3) universal acceptance of IDN TLDs. Both the ccNSO and GNSO have extended this charter to continue into 2012. | 2009 July-23 | Ongoing | WG | Following are updates on each of the three key areas of work: - Single Character IDN ccTLDs and gTLDs. The GNSO and ccNSO both approved a Final Report. In August the Board requested further advice from the SOs and ACs. New advice was offered by the SSAC, SAC 52, see, http://www.icann.org/en/committees/security/sac052.pdf. On 24 February, the GNSO and ccNSO Councils submitted a response to the Board reiterating support for the introduction of single character IDN TLDs and asking clarifying questions, see http://gnso.icann.org/mailing-lists/archives/council/msg12678.html. - Following posting of a final Integrated Variant Issue Report on Feb 20, http://www.icann.org/en/topics/idn/idn-vip-integrated-issues-final-clean-20feb12-en.pdf, the JIG is now considering a revised IDN Variant Program Plan (posted 25 May, reply comments due 15 June, see: http://www.icann.org/en/news/public-comment/idn-variant-tld-revised-program-plan-04may12-en.htm). The JIG has prepared a letter on IDN Variant TLDs which is expected to be submitted to the GNSO and ccNSO Council in time for consideration at the Durban meeting. - Universal acceptance. The JIG is working on its Final Report on this topic. - The WG has reduced its number of meetings from every two-weeks to once a month. |
| Joint Security and Stability Analysis Community Working Group (DNS Cert) ccNSO Co-Chair: Jörg Schweiger, .de GNSO Co-Chair: M. O’Connor Staff: B. Boswinkel, J. Hedlund | 2010 June | Ongoing | WG | The DSSA has provided a Phase I Draft Report to the Chartering SOs and ACs – including the GNSO. The DSSA-WG sent the Phase 1 Draft Report out for Public Comment through Toronto and will analyse comments received. The WG will meet in Durban to consider the latest update from the consultants preparing the report for the Board DNS Risk Framework Management WG. |
| ccNSO Study Group on the Use of Names for Countries and Territories (ccNSO-NCTSG) Chair: Paul Szyndler, .au Staff: B. Boswinkel This group of ccNSO, GNSO, GAC and ALAC representatives is considering policies and procedures to allocate TLD strings that are either associated with Countries and Territories (i.e. by inclusion in the ISO 3166-1 list) or are otherwise considered representations of Country or Territory names. | 8 Dec. 2010 | ongoing | Study Group / Community | The focus is on stocktaking current policy approaches, postulating the types and categories of strings that could be interpreted as country or territory representations and analysing what happens when policies are applied to the identified strings. To this end, UNESCO was tasked to conduct a survey which was sent to 39 UNESCO Member States (July 2012). 13 responses were received to date. The Study Group has now published its proposed Final Report for public comment (see http://www.icann.org/en/news/public-comment/unct-final-02jul13-en.htm). Comments may be submitted until 2 August, followed by a reply period which will close on 30 August. |

| Approved GNSO PDP Recommendations - Status (For Information Only) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Adopted | Target Date | Who holds Token | Pending action/status |
| IRTP Part B PDP Adopted Recommendations |  |  |  |  |
| 5. Promotion by ALAC and other ICANN structures of the measures outlined in a recent SSAC report: A Registrant's Guide to Protecting Domain Name Registration Accounts (SAC 044). (See http://gnso.icann.org/resolutions/#201106 for text of resolution) | 22 June 2011 |  | SOs/ACs | Chair of the GNSO Council has sent messages to the Chairs of ALAC, SSAC, ccNSO, GAC, ASO (see http://gnso.icann.org/mailing-lists/archives/council/msg11736.html) to inform them about the recommendation and open discussions. |
| IRTP Part B Recommendation #9 – part 2 The GNSO Council resolved in Singapore that prior to consideration of the recommendation which states: "denial reason #7 should be replaced by adding a new provision in a different section of the IRTP on when and how domains may be locked or unlocked", the GNSO Council requests ICANN Staff to provide a proposal for such a new provision, taking into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report - (Recommendation #9 - part 2). Upon review of the proposal, the Council will consider the recommendation. | 2011-Jun-22 |  | Staff | The ICANN Board adopted the recommendation and staff proposal at its meeting in Costa Rica. ICANN Staff has started working on the implementation of the recommendation. |
| IRTP Part B Recommendation #8 The GNSO Council resolved in Singapore that prior to considering a recommendation to standardize and clarify WHOIS status messages regarding Registrar Lock status, the GNSO Council asked staff to provide a proposal to ensure that it is technically feasible to implement this recommendation. Staff should take into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report). (IRTP Part B Recommendation #8). The goal of these changes is to clarify why the Lock has been applied and how it can be changed. Upon review of the proposed plan, the Council will consider whether to approve the recommendation. | 2011-Jun-22 | May 2012 | Board | The ICANN Board adopted the recommendation at its meeting on 6 May (see http://www.icann.org/en/groups/board/documents/resolutions-06may12-en.htm#1.5). ICANN Staff has now published the proposed implementation plan for public comment (see http://www.icann.org/en/news/public-comment/wisp-10may13-en.htm). Comments can be submitted until 31 May, followed by a reply period. |
| IRTP Part C Recommendations |  |  |  |  |
| The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see http://gnso.icann.org/en/resolutions#20121017-4). | 17 Oct 2012 | Dec 2012 | Board | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December (see https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a). As instructed by the GNSO Council, an Implementation Review Team has been formed and a first meeting to consult with staff on the development of the implementation plan is scheduled for 3 July. |

| Outstanding Recommendations for Council Action |  |  |
| --- | --- | --- |
| Description | Who holds Token | Pending action/status |
| None |  |  |