## Slide 1: GNSO Improvements Top Level Plan
29 May 2009
Plan distributed 22 May by Avri

## Slide 2: GNSO Planning Team Members
Avri Doria (NomCom Appointee, GNSO Council chair)
Chuck Gomes (RyC, GNSO Council vice‑chair)
Olga Cavalli (NomCom Appointee)
Philip Sheppard (Business Constituency)
Robin Gross/Milton Mueller (NCUC)
Ute Decker (IPC)
Wolf‑Ulrich Knoben (ISCPC)
No current appointee (Registrar Constituency)

## Slide 3: ICANN Planning Team Members
Susan Crawford (BGC Liaison)
Denise Michel (VP, Policy Development)
Liz Gasster (Sr. Policy Counselor)
Robert Hoggarth (Sr. Policy Director)
Penelope Wrenn (Policy Communications Director)
Glen De Saint Géry (GNSO Secretariat)

## Slide 4: Planning Team Roles
Propose a work structure for implementing:
  Non-contentious operational changes recommended by the BGC WG
  All recommendations as appropriate once the full plan has been adopted by the Board
Monitor implementation progress & report to Council and Board
Assist implementation committees, teams & working groups

## Slide 5: Planning Committee Recommendation
Form two standing committees (SCs):
  GNSO Process Standing Committee
  Operations Standing Committee
Focused on processes and practices, not on gTLD policies
Milestones set by SC & approved by Council
Charters approved initially by Council and reviewed by Council annually
May be terminated by Council at any time
Recommended start date: 27 June 2008

## Slide 6: Standing Committee Membership
Approved by Council
Maximum 12
May be mostly Councilors but not restricted to Councilors
Could eventually include representatives from emerging constituencies

## Slide 7: Role of Standing Committees
Create implementation work teams
Coordinate efforts of work teams
Oversee development of implementation plans
Make recommendations concerning processes and methods involved in the transition of the GNSO
Serve as ongoing GNSO process review body

## Slide 8: Process Standing Committee (SC)
Responsible for recommending and reviewing any processes used within the GNSO and its council for developing policy recommendations
Immediate goal: initiate the process for developing recommendations for all process changes needed to meet the requirements of the BGC WG report and final Board recommendations
Once the first set of changes has been implemented, responsible for reviewing the functioning of the new processes and for recommending any further changes

## Slide 9: Process SC Initial Work Items
Establishing new rules for the Policy Development Process (PDP)
Establishing procedures and guidelines for the functioning of the policy Working Groups
Possible Approach
SC could establish 2 work teams.
SC would coordinate & assist 2 teams.

## Slide 10: Proposed Membership of Process SC
GNSO council chair and/or vice chair
1 representative from each constituency (need not be a Council member)
1 NomCom appointee
Liaison or an appointed representative from ALAC and GAC
GNSO secretariat
1 ICANN policy staff representative

## Slide 11: Process SC Teams
It will be the task of the committee once it is established and possibly the teams it creates to establish team charters.
To facilitate this task, the planning document references some ideas for consideration by the SC.

## Slide 12: Operations Standing Committee (SC)
Responsible for coordinating, recommending and reviewing changes to certain operational activities of the GNSO and its constituencies
Immediate goal: develop recommendations to implement the “non‑contentious” operational changes recommended in the Report
Responsible for implementing whatever structuring plan (if any) is ultimately approved by the Board
Responsible for reviewing and assessing the effectiveness of changes made and for recommending further operational enhancements as warranted

## Slide 13: Proposed Operations SC Membership
GNSO council chair and/or vice chair
1 representative from each constituency
1 NomCom appointee
1 representative from any constituencies formally involved in the process of formation (once the process for forming a new constituency has been established)
Liaison or an appointed representative from ALAC and GAC (as appropriate)
GNSO secretariat
1 ICANN policy staff representative

## Slide 14: Possible Operations SC Approach
SC may create separate teams to take on the work of distinct operational areas.
Possible teams:
  GNSO Operations (if needed)
    Develop a proposal for Council consideration on GNSO operations‑related recommendations
  Enhance Constituencies
    Develop a proposal to implement recommendations focused on enhancing constituency operations
  Improve coordination with other ICANN structures
    Develop a proposal to improve communication and coordination

## Slide 15: Operations SC Special Teams
Some recommendations may lend themselves to being addressed through the establishment of special focus teams:
  Examples: web-site redesign; project management tools; document management tools; etc.
  These teams would likely consist of special experts depending on the subject matter.

## Slide 16: Operations SC Teams
It will be the task of the committee once it is established and possibly the teams it creates to establish work team charters.
To facilitate this task, the planning document references some ideas for consideration by the SC.

## Slide 18: Next Steps
Initial discussion today
List discussion in coming weeks including:
  Suggesting edits
  Identifying possible SC members
Informal community review
Final discussion and revisions on Saturday in Paris
Council approval of plan in Open Council Meeting on 25 June
Initiation of SCs on 27 June

## Slide 19: Q&A