## Slide 1: ALAC WG on IPv4v6
Feb 9 2008
New Delhi

## Slide 2: Goal
To give a clear picture of the IPv4 depletion and the IPv6 migration issues to the end user
To convey the users’ messages and opinions back to the technical community and the decision makers

## Slide 3: Objectives
To create a useful tool to help engage and inform the Internet Using Public about the issue
To advise ICANN Board on the issue from the perspective of the Internet Using Public

## Slide 4: Background Description
IPv4 address pool is estimated to expire sometime around 2010.
Measures are taken to address this issue by technical community including NRO/address community, but much has to be done by all operators of global Internet and decision makers concerned.
ALAC made a statement at a ASO Workshop on IPv6 Migration at ICANN LA meeting in Nov 2007, calling for further collaboration
Workshop on IPv4v6 was organized at IGF in Rio, December 2007 including members of ALAC, ICANN technical and business community members

## Slide 5: Main Issues
IPv4 addresses are running out, but IPv4 network is not going away
IPv6 has to co-exist with IPv4 network – not transition or migration
How do we do it without breaking the Internet’s end to end connectivity?
Challenges are broad and deep
  Technical, operational, economic, policy, business, user

## Slide 6: Target Group
Internet Using Public
Global Operational Community
ICANN Board
Policy makers and experts in policy arena

## Slide 7: Action Plan

## Slide 8: List of activities
Organize workshop at coming ICANN meetings starting from Paris
  Invite experts/stakeholders and policy makers
  Ask questions of mutual interest
  Monitor the developing activities

## Slide 9: Task division
Planning
Implementation
  Information gathering
    Technical issues
    Operational issues
    Policy issues
    Economic/business issues
    Social/user issues
  Outreach

## Slide 10: Timeframe – for 2008
Feb Finalize Action Plan
  Ask for Issue Paper?
May prepare Short Position Paper?
Jun Workshop at Paris meeting
Nov Workshop at Africa meeting
Dev Workshop at IGF in Delhi?

## Slide 11: Additional resources

## Slide 12: Cost for this activity

## Slide 13: Partners involved
ASO/NRO
People from Operators Community
  NANOG, SANOG etc.
ISPs & ASPs – Google, Yahoo, etc.
Vendors
Governments/GAC?
Policy Makers

## Slide 14: List of expected outcomes and outputs
Clear understanding of the issue
Concerted Actions taken by all stakeholders concerned
  Address community
  Operators: ISP, ASP, IX etc.
  Policy Makers
  Business Users
  Public Users

## Slide 15: Evaluation indicators and instruments