## Slide 1
GNSO Improvements
Status
Click each box to view latest status; Click this box to see Next Steps.
Updated: 18 October 2010
Note: This status format is a relatively new innovation proposed by the ICANN Board’s Structural Improvements Committee (SIC) and developed by ICANN Staff. The Staff welcomes any community feedback and suggestions for improvements at: policy-staff@icann.org.

## Slide 2
GNSO Council Restructure

## Slide 3
Adopt a WG Model

## Slide 4
Enhance & Support SGs/Constituencies

## Slide 5
Revise the Policy Development Process

## Slide 6
Improve Communications & Coordination

## Slide 7: GNSO Improvements Next Steps (Q4 2010)

## Slide 8: GNSO Improvements: Key Milestones
Q2 [2008] Q3 Q4
Q1 Q2 [2009] Q3 Q4
BGC Report
Q1 Q2 [2010] Q3 Q4
Work Teams Formed (Mexico City)
Board Approved Bylaws & Transitional SG Charters
New GNSO Council & Bicameral House (Seoul)
Council Approved GNSO Operating Procedures–v1.0 (Seoul)
List of “Toolkit” Services Approved by Council
CSG Work Team Task #1 Final Report Approved by Council
PDP Work Team Published Initial Report
Legend:
GNSO Council Restructure
Enhance & Support SGs/Constituencies
Adopt a Working Group Model
Improve the Policy Development Process
Improve Communications & Coordination
Black Text = Completed
Yellow Text = Scheduled
Council Approved CCT Work Team Final Report
Board Review of Constituency & SG Charters
Resolve Individual User Membership in Constituencies/SGs
WG Work Team Published Draft Guidelines
Resolve NCSG Structural Design Proposal
Staff Program & Project Support Plans Completed
Council Implementation Plan Approved
Work Teams Complete Final Deliverables for OSC/PPSC Approval
Note: This status format is a relatively new innovation proposed by the ICANN Board’s Structural Improvements Committee (SIOC) and developed by ICANN Staff. The Staff welcomes any community feedback and suggestions for improvements at: policy-staff@icann.org.